## Slide 1
Program Title
Air Force Review Board (AFRB) Date
Rank, Name
Office Symbol
Date
Development RFP Release Template
Updated: April 2018
"CLASSIFICATION/FOR OFFICIAL USE ONLY/Pre-Decisional"
See Notes Pages
for additional
information
Notes: To schedule a HQS AFRB please contact the AFRB Secretariat (SAF/AQXE, Acquisition Center for Excellence (ACE): Mr Stan Armstead at 571-256-1804 or Captain Nick Baker at 571-256-0407. The earlier you request a meeting the more likely you will get the dates you need.
AS A REMINDER CHARTS ARE DUE TO THE SECRETARIAT 7 DAYS AHEAD OF THE BRIEFING OR THE MEETING MAY BE CANCELLED.
The purpose behind this template is to provide guidance on the issues and requirements to address at MS B. Each briefing will be different depending upon the nature of the program. Only brief those items that are important for the MDA to make a decision. All briefings should have less than 40 charts (not counting back-ups) to be briefed to SAF/AQ within the one hour and one-half hour that will be scheduled for the meeting.
If you have questions in preparing your briefing please contact your local Acquisition Center of Excellence (ACE) for guidance.
  Wright Patterson AFB DSN: 785-5518/COMM: 937-255-5518
  Hanscom AFB DSN: 845-1660/COMM: 781-225-1660
  Eglin AFB DSN: 875-0526/COMM: 850-883-0526
  Warner Robbins DSN 468-0274/COMM: 478-926-0274
Hill AFB DSN: 777-7999/COMM: 801-777-7999 or-777-5538
Tinker AFB DSN: 884-2791/COMM: 405-734-2791
  Los Angeles AFB (SMC/PID) DSN: 633-1534/COMM. 310 653-1534
  SAF/AQXC Commercial: 202-404-3285 (If you have recommendations to improve the ASP template)
Pls mark documents as follows for ACAT I programs per OSD/GC recommendations "CLASSIFICATION/FOR OFFICIAL USE ONLY/Pre-Decisional/"

## Slide 2: Briefing Outline – Key Items
BLUF
Program Description/Overview
Requirements
TMRR Phase status
  Events to Development RFP Release
Schedule
Funding
Approved Acquisition Strategy (Framing Assumptions) and RFP
Risks
Document Status
Way Ahead
Notes: While it is not mandatory, nor possible, in an hour and a half to address all the subjects, it is prudent to be prepared to brief or address all topics.

## Slide 3: “Bottom Line Up Front (BLUF)” (Decisions Requested & Key program information)
Purpose
  Program Progress to date
  Release RFP for EMD (and Production)
    RFP is executable and ready for release
    AS incorporated into RFP (any changes?)
Decisions you are requesting (examples)
  Approval to release RFP to OSD
  Approval to proceed to OIPT and DAB/ITAB (if OSD is MDA)
  Approve Applicable delegations/waivers (e.g., source selection authority)
List Outstanding Issues
  Issue 1-- Aggressive schedule for award
  Issue 2--TRL level 5 for one of 6 critical technologies

## Slide 4: Program Description/Overview
Required Funding
Description
Acquisition Strategy
  Evolutionary Acquisition
  Source Selection
    Potential sources
      Raytheon Missile Systems, Tucson
      The Boeing Company, St Louis
  EMD-Cost Plus Incentive Fee (CPIF)
  Production
      Lots 1-3 -- FPI(F)
      Lots 4-5 – Fixed-Price NTE w/ Economic Price Adjust
  250-lb Class, Precision Guided, Air-to-Ground Munition
  Kill Mobile/Fixed Targets Thru Weather from Standoff
  Uses Tri-Mode Seeker & Dual-Band Data Link (Link 16 + UHF)
  Services: USAF, DoN
  Threshold Platforms: AF--F-15E; USN--F-35C
  IMD sensitive (for clarification see notes)
  ACAT Level: ID
  MDA: USD (AT&L)
  PEO: AFPEO (Weapons), Maj Gen Blaster
  PM: 918 ARSG/CC, Col Boomer
  AF/DoN Committed to Service Cost Position
  Approved 21 Sept 15
Gateway(s)
65 North
Spot Beam Required on one Gateway to achieve XDR throughput
Polar Coverage Area
above 65o Lat north
Spot Beams Service Polar Users
GIG
Teleports
Adequate Funding in the FYDP
FYxx will required rephasing of funds in next PB
Full Funding memo required
Operational Need
Notes: Intelligence Mission Data (IMD). DoD intelligence used for programming platform mission systems in development, testing, operations, and sustainment including, but not limited to, the functional areas of signatures, EWIR, OOB, C&P, and GEOINT.
IMD-dependent programs. Any acquisition programs that will require IMD (e.g., programs that carry out combat identification, ISR, and targeting using, but not limited to, signatures, EWIR, OOB, C&P and GEOINT.)

## Slide 5: Requirements
Operational Requirements
  When Approved (AOA, ICD/CDD/CPD, CONOPS)
  Key KPPs—fully identified and clearly stated?
  Incremental Requirements?
    All increments contained in one CDD?
  How does the program baseline compare to validate requirements
  How will program achieve information assurance requirements? (see footnotes)
  Explain how changes in threat data will be handled in the management of the RFP/Contract
    How is it handled during test in the contract?
Operational Capabilities/Impacts
  Capabilities / missions (today & future)
    Relationship to established roadmap(s) / architecture(s)
    Family of Systems (FOS) / System of Systems (SOS) / Complementary Systems
      How are these relationships handled in the RFP/Contract
Notes: This particularly import for Command, Control, Communications, Computers, Intelligence, Surveillance, and Reconnaissance systems; and information technology programs that depend on external information sources or provide information to other DoD systems.

## Slide 6: TMRR Phase Status
Status of technology maturation and risk reduction efforts
Competitive Prototype status
Capability requirements trade space and understanding of the priorities within that trade space.
Technical, cost, and schedule risks
  Adequacy of the plans and programmed funding to mitigate those risks
Acquisition Documents at the “Draft Approved” phase

## Slide 7: DoD 5000.02 Tailoring Strategy
Discuss overall 5000.02 tailoring strategy
  Is program requesting approval for specific tailoring at this meeting?
  If not, why?
Recommend area(s) that program intends to target for tailoring in future
Identify necessary dates & timelines to return for tailoring approval

## Slide 8: Events to Development RFP Release
ACE Murder Board #2 20 Jan 16
JAG Review 3 Feb 16
MIRT #2 17 Feb 16
Risk Workshop 18 Feb 16
WL/PK Review 24 Feb 16
SSP Approval 3 Mar 16
Business Clearance 4 Mar 16
MDA Approval to Release RFP 4 Mar 16
Dev RFP Release 7 Mar 16

## Slide 9: Sample Program Schedule
I n t e g r i t y - S e r v i c e - E x c e l l e n c e
F-35B & C
Integration
CTV
GTV
EMD
SDB-II
Development
Timeline*
CDR
PDR
SRR
1st AUR Avail
RISK REDUCTION
2 COMPETITIVE CONTRACTS
MS-B
F-15E Suite 7E OFP
DT IT OT
F-15E APG-70 GMTT
Dev & Test
F-15E
Integration
Normal attack
CAM/SAL
F-35 Block 3.X OFP
DT IT OT
F-35B
FISCAL YEAR
2008
2009
2010
2011
2012
2013
2014
2015
2016
2017
2018
2019
F-35C
JROC
AOA
1998-2000
To Complete
FY19-FY23
12,966
Normal Attack
OTRR
CAM/SAL
OTRR
F-35B & F-35C
OTRR
F-15E
RAA
F-15E
Full
Capability
F-15E
RAA
*Will be updated after
contract award
F-35B/C
Initial Fielding
2020
DT IT OT
BRU-61/A
Dual Power BRU-61/A
Delta Qual BRU-61/A for F-35 environment
MS-C
FRP
PRODUCTION
LRIP 1
LRIP 2
LRIP 3
LRIP 4
FRP 1
FRP 2
144
250
390
550
1050
Quantity
SVR
PCA
SVR
DT IT OT
83 mos
83 mos
59 mos
CA/Lot
Excerpt from 28 Jul 09 SDB II CDD, Cpt 11:
Required Assets Available (RAA): SDB II RAA is the capability to arm twelve (12) F-15Es with two (2) fully loaded BRU-61/A carriage systems each for 1.5 sorties (144 assets total)
DoN Assets for Initial Fielding: Initial quantity of SDB II weapons required is 90 weapons and 22 carriage systems based upon one ten (10) plane squadron with two (2) fully loaded carriage systems each plus ten spare weapons.
EOA
OA
IPR
Post-CDR
Report
Note: Due to delay of MS B, shaded blue region will move right accordingly
NEED TO ADD TOP LEVEL CRITICAL PATH
Notes: Identify Major Schedule Drivers:
Obsolescence?
Are we trying to beat someone in this competitive space, and what’s the value proposition for doing so?
What technical issues pace the project?
Note: Program schedule shall address critical path

## Slide 10: Schedule to Contract Award
DRAFT RFP RELEASE
FEDBIZOPS SYNOPSIS OF FORMAL RFP
PRESOLICITATION CONFERENCE (if Comp)
PEER REVIEW
RFP RELEASE
PREPROPOSAL CONFERENCE (if Comp)
PROPOSALS RECEIVED
FACT FINDING/DISCUSSIONS
COMPETITIVE RANGE BRIEF (if Comp)
FINAL PROPOSAL REVISIONS/DISCUSSIONS
MILESTONE B
CONGRESSIONAL NOTIFICATION
CONTRACT AWARD (see footnotes)
DEBRIEFINGS (if Comp/if requested)
Notes: There are milestones related to the activities leading to contract award like RFP review, approval for release, source selection period, JAG review, etc.
Contract Award – Allow adequate time during source selection for the MIRT, Peer Reviews and a MS decision.

## Slide 11
Mandatory
Notes: Notes:
+Enter values in the unshaded (white) annual and to-complete cells only. The rest of the data is calculated automatically. The spreadsheet cells will round to the nearest hundred thousand dollars ($0.1M).
+Delete any appropriation sections that have no budgeted or required costs.
+Programs must use footnotes to state source of "Required" estimate, O&S service life projection, O&S time horizon (first year of O&S – last year of O&S) & cost categories, and any RDT&E-funded quantities (if any). See Figure 1.
+Program offices are to use the latest version of the program funding template. Regularly check the Acquisition, Technology and Logistics (AT&L) Defense Acquisition Board (DAB) online calendar website (https://ebiz.acq.osd.mil/DABCalendar/) for the most current Integrated Product Team (IPT) Program Funding template. The template is updated as Programming, Planning, Budgeting, and Execution System (PPBES) events occur.
Definitions:
Primary Line Items: In the header of each section, list the primary budget line item(s) that fund the program currently and in the FYDP. For RDT&E, MILCON, and O&M, include appropriation (consistent with DAMIR reporting), budget activity and program element. For procurement, include appropriation, budget activity and line item. Some programs have smaller amounts of funding in secondary line items that need not be listed. Footnotes may be used for clarification/amplification.
Prior: President’s Budget (PB) position submitted prior to the Current budget position. Although the President only submits the FYDP to Congress, the cells for the next fiscal year and “To-Complete” should be populated for the investment appropriations using the values reported in the Selected Acquisition Report or latest DAES associated with that PB (if available).
Current: Latest approved Service POM/BES budget position or approved PB.
+During a normal PPBES cycle (PB submitted in the first Tuesday of February each year), use POM position from August through January; Use PB position from February through July.
+When the DoD Appropriation is enacted, programs should update that cell of all the "Current” PB funding and quantity rows to reflect the actual appropriated amounts.
Required: Latest estimate of funds required to successfully execute program, i.e., support the Warfighter and not simply match available budget Total Obligation Authorities (TOAs). Typically, this would reflect the Will Cost estimate, Service Cost Position (SCP), or PEO-supported Program Office Estimate (POE) that has not yet been validated by a Service Cost Agency or the CAPE. Note: total required quantity is the acquisition objective recognized by the Joint Requirements Oversight Council (JROC) or similar body and would be reflected in the program's Acquisition Program Baseline (APB) or similar document but may not be reflected in the budget due to affordability or funding issues.
System O&M: In this section, list the O&M-funded costs from initial system deployment through end of system operations. Include all costs of operating, maintaining, and supporting a fielded system. Specifically, this consists of the costs (organic and contractor) of equipment, supplies, software, and services associated with operating, modifying, maintaining, supplying, training, and supporting a system in the DoD inventory. Do not include acquisition-related O&M, and non-O&M O&S costs such as military personnel, and investment-funded system improvements. Also, do not include disposal costs, which represent a separate phase of the program life cycle. Please address questions on the O&M requirements to the OSD(AT&L)/L&MR point of contact listed below.
Total Required Acquisition (BYXX$M):
+Current Estimate of Total RDT&E, procurement, MILCON and acquisition-related O&M in base-year dollars as reported in the program's latest approved POM budget position, approved PB, or quarterly DAES submission, whichever is most current.
+The percentage displayed is the portion of the Acquisition cost out of the sum of Acquisition and O&S costs.
+Revise “BYXX$M” to reflect the 2-digit program Base Year (e.g., BY16$M). Use the Base Year specified in the current Acquisition Program Baseline (APB). For unbaselined programs (or if seeking a new or revised APB), use the budget year (e.g., BY18$M for PB18).
Total Required O&S (BYXX$M):
+Current Estimate of Total Operating and Support costs in base-year dollars as reported in the program’s quarterly DAES (if applicable). See Figure 2.
+A footnote should identify the projected service life.
+Disposal costs should not be included in this value.
+The percentage displayed is the portion of the O&S cost out of the sum of Acquisition and O&S costs. This value should not include disposal dollars.
+Revise “BYXX$M” to reflect the 2-digit program Base Year (e.g., BY16$M, IAW the instructions above for Total Required Acquisition).
Curr Est (APUC): Program Manager’s current estimate of Average Procurement Unit Cost, in base-year dollars (total procurement divided by procurement-funded quantities). The APUC should match the values reported in the program's latest approved POM/BES budget position, approved PB, or quarterly DAES submission, whichever is most current.
Curr Est (PAUC): Program Manager’s current estimate of Program Acquisition Unit Cost, in base-year dollars (total RDT&E, procurement, MILCON and acquisition-related O&M divided by total quantity). The PAUC should match the values reported in the program's latest approved POM/BES budget position, approved PB, or quarterly DAES submission, whichever is most current.
Δ Current: This is the program’s APUC or PAUC current estimate (as defined above) divided by the program’s current APB Unit Cost Reporting (UCR) baseline, as applicable. Figure 3 illustrates where this information resides in the program’s DAMIR DAES.
Δ Original: This is the program’s APUC or PAUC current estimate (as defined above) divided by the program’s original APB UCR baseline, as applicable. See Figure 3.
Points of Contact:
Army Programs:
Allen Johnson, OSD(AT&L)/ARA
allen.m.johnson44.ctr@mail.mil
703-697-5384
Navy Programs:
CDR Joseph Mitzen, OSD(AT&L)/ARA
joseph.b.mitzen.mil@mail.mil
703-697-8020
Air Force Programs: Matthias Maier, OSD(AT&L)/ARA matthias.r.maier.ctr@mail.mil 703-614-4030
Agency & Department-wide Programs:
Mr. Russ Vogel, OSD(AT&L)/ARA
russell.a.vogel.civ@mail.mil
703-697-1786
O&S Section:
Ms. Molly Mertz, OSD(AT&L)/L&MR
mary.m.mertz.civ@mail.mil
703-614-6137

## Slide 12: Acquisition Strategy
Framing Assumptions (see back-ups for format)
In general terms what is the acquisition strategy?
  Evolutionary, incremental, buy to budget
    EMD, EMD plus LRIP
  Multiple source development with down select
  Advance Procurement
  Breakout of components
  Competitive, sole source
    Source selection--Section M requirements
    Source Selection--Section L requirements
  Future competitive buys—production (EOQ), sustainment

## Slide 13: How is the AS incorporated into the RFP? Major Contract (s) Planned
AS
What the basic contract buys; options
  IDIQ vs single award
Identify the contract type(s) and period(s) of performance
Qty per year, total production and LRIP qty.
Statement of work and specifications
MOSA
RFP
Clins 001 emd cpif start date, finish date
Clin 0002 data, nsp
Clin 003 option, 100 units, exercise date, completion date
program requirements to be bid against are firm and clearly stated

## Slide 14: Source Selection
AS
Source selection evaluation approach
  Source Selection (Section M) criteria.
  Section L requirements
    Also consider briefing how program risks, technolgy, schedules are being handled
List potential sources
Subcontract competition
Small business subcontracting plan / small business participation
RFP
Section L & M
Provide Copies of RFP Sections L and M

## Slide 15: Incentives
AS
Contract incentives:
  specific incentive structure
Where are testing and systems engineering requirements and what do they require
ID engineering activities in RFP (eg., CDR) and contractor to demonstrate R&M achievements and MOSA/OSA (e.g., Mil-Stds)
How are KPPs incorporated into the contract? (threshold goal)
RFP
Contract type
  Share ratios
Incentives for schedule or performance and clauses
SEMP DI-MGMT-81024
Special Clauses
Sys-Spec 8000

## Slide 16: AS Vs RFP
AS
Sustainment Strategy.
  Government vs contractor support
  Overview of the sustainment-related contract(s)
  Interim Contract Support (ICS)
Technical Data Rights Strategy (Data Management Strategy)
RFP
What provisions in the contract to track contractors cost performance?
What contract clauses and data deliverables for data rights—eg., mil-dtl-31000C and CDRL DI-SESS-81000C

## Slide 17: AS Vs RFP
AS
Special clauses
Identify any changes from the approved Acquisition Strategy
RFP
Funds management, contingent liabilities (award fee, etc), Limitation of Government Obligation, FMS, Warranties
CSDR
  Approved Tailoring incorporated into RFP
  Any FAR deviations

## Slide 18: Risk Assessment & Management
 | 1O 1K | 1A 1T 1U | 1F | 
 | 1L 1M 1S 1Y | 1E 1I 1N 1V 1X |  | 
1P |  | 1B 1D 1J 1R IW | 1C | 
1O- Source Selection schedule
1K- Type 1 training at multiple locations
1L- Long-term Sustainment
1M- MOAs with installation bases
1S- Technical shortfalls during installations
1Y- IFF test sets availability
1E- A/C configuration variances during development
1I- GFP Delay
1N- A/C variances during installations
1V- Kit Production
1X- FY18 production funds rescission
1P- GATM award delay
1B- Acquisition documents
1D- DSOR delay
1J- Mode 5 program delay
1R- Raytheon upgrade capacity
1W- CFT capabilities
1C- Fiscal phasing
Revised 9 Oct 15
Notes: 18

## Slide 19
 | 1K |  | 1F 1O | 
 | 1L 1M 1Y | 1E 1I 1J 1N 1V 1X | 1U | 
1E - AC Config vary in Dev
1I - GFP Delay
1J - Mode 5 Program Delay
1N - Tech/Config issues in Prod
1V - Initial Spares
1X - Schedule
Initial Risk Workshop/Assessment: 12 Aug 15
Latest Risk Assessment: 18 Feb 16
1L - Long Term Repair/Supply Chain
1M - Establish Agreements
1Y – IFF Test Set Availability
1K - Type 1 Training
Program Risks – RFP DP
1F – ATO Delayed
1O - Source Selection
Not Likely
Low Likelihood
Likely
Highly Likely
Near Certainty
Likelihood
Min
Mod
Minor
Ser
Major
Consequence
1U - Delay to Stage 4 RFA
Notes: 19

## Slide 20: DRFP MS Document Status
Documentation | S/R* | Status | Comments
Acquisition Decision Memorandum (ADM) | R | In draft form | 
Acquisition Program Baseline (APB) | S/R | In-Work | Program Office will finalize after AFCAA
Acquisition Strategy | S/R | Complete | 
Affordability Analysis (update) | R | In Coord | In SAF 3-ltr Coord
Analysis of Alternatives (AoA) (update) | S | Final | 
Bandwidth Requirements Review | S | Final | .
Capability Development Document (CDD) | R | Final | 
Concept of Operations/ Operational Mode Summary/ Mission Profile | R | Complete | 
Core Logistics Determination/Core Logistics and Sustaining Workload Estimate | S | In-work | AFMC should complete by end of June
Cost Analysis Requirements Description (update) | R | Final | 
Complete | On-Track | Minor Issues | Major Issues
* S=Statutory, R=Regulatory
"PMs will address their streamlining
documentation strategy"

## Slide 21: DRFP MS Document Status
Documentation | S/R* | Status | Comments
Development RFP Cost Assessment | R | In work | Complete by 30 June
Economic Analysis (MAIS) | S | Completed | 
Exit Criteria | R | Final | 
Information Support Plan Net-Centric Data Strategy | R | Complete | 
Life Cycle Mission Data (update) | R | In-Work | Update to be complete by 30 June
Life Cycle Support Plan (update) | R | On-track | Awaiting AQD coordination
Low-rate Initial Production (LRIP) Qty | S | Complete | 
Manpower Estimate | S | Complete | 
Problem Statement (DBS) | R | Complete | 
Program Protection Plan (update) Cybersecurity Strategy | R S | Complete | 
Request for Proposal | R | Complete | 
* S=Statutory, R=Regulatory
Complete | On-Track | Minor Issues | Major Issues
"PMs will address their streamlining
documentation strategy"

## Slide 22: DRFP MS Document Status
Documentation | S/R* | Status | Comments
Should Cost Target | R | Complete | 
System Threat Assessment Report (Update) | R | Final | 
Systems Engineering Plan (Update) Item Unique ID implementation Plan Corrosion Prevention Control Plan (Update) Manufacturing Risk and Readiness | R | In-Work | In work to finalize 30 May.
Technology Readiness Assessment | S | complete | 
Test & Evaluation Master Plan (update) | R | Complete | DOT&E signed off on 15 May
* S=Statutory, R=Regulatory
Complete | On-Track | Minor Issues | Major Issues
"PMs will address their streamlining
documentation strategy"

## Slide 23: Way Ahead
OIPT scheduled for XX Date
DAB scheduled for XXX Date

## Slide 24
BACK UP SLIDES

## Slide 25: SAMPLE APT Framing Assumption #1
Expectations
Implications
Framing Assumption
Purpose-built will be competitive with existing designs
Basic aircraft and training system designs will be complete through vendor-conducted CDRs
Enter at MS B
Limited EMD of “deltas” to meet spec
PDR and competitive prototype waivers applicable*
Best-value source selection must consider risk
Contractor flight data to validate performance
Single step to full capability
Single award for EMD, Prod and ICS
RAA in 2023
FOC in 2031
“PRE-DECISIONAL – NOT FOR RELEASE”
See Notes Page for more examples of framing assumptions
Notes: Examples of other Framing Assumptions:
Adequate industrial base for competition
Technology well in hand
Requirements achievable
Aggressive schedule is risky but achievable
SPO will have personnel to handle integration role
“Back to basics” would help solve technical and mgt issues
Separate space and ground segments would provide “best of breed”
Incremental/block approach
Capability Insertion Program, graceful growth
Incentivize for mission success, on-time/on-cost delivery, high
confidence approach

## Slide 26: Program Org Chart
OSD/AT&L
SAF/AQ
PEO
Lt Gen JP Jones
PM
Col John Smith
Program
Control
Maj D. MacArthur
Contracts
Ms. Jane Smith
Sys Eng
Maj Kelly Johnson
Test
Maj C. Yeager
Test IPT
2 Captains
1 GS-12
5 Contractors
PC IPT
2 Captains
1 GS-12
5 Contractors
Contracts IPT
2 Captains
1 GS-12
Sys Eng IPT
2 Captains
1 GS-12
5 Contractors
ACC/A5XX
Col B Martin
OO-ALC/XYZ
Col Al Griggs
User
Depot
Sample
PSM
Lt. Col T. Jones
Support IPT
1 Captain
1 GS-12
4 Contractors
Notes: Use existing program org charts so long as they show from MDA through PM and major IPTs within the program office.
In no case shall there be more than two levels of review between the Program Manager and the Milestone Decision Authority in accordance with DODD 5000.01, DODI 5000.02, and AFPD 63/20-1.
Include in your chart the Program Control Office, if you have one.