| Record of Changes |
| --- |
| Version | Effective Date | Summary |
| 1.0 | 8 Mar 2016 | 24 Feb 2016 S&P board directed document changed from Process Standard to Process Guide at 24 Feb 2016. Document revised to remove mandatory ACAT 1 pre-initial MS requirement, metrics references and to make minor format and content changes to conform with revised process template approved at the same S&P board meeting. |

Program Sufficiency Review (PSR)

- Description

The Program Sufficiency Review (PSR) is a process of conducting assessments culminating in a final outbrief of the results of those assessments to obtain approval of a program baseline (PB).  The PSR integrates findings from multiple assessments and provides an opportunity at the outbrief for communication and crossfeed of information obtained from these assessments to support program decisions, establish executable budgets, and proactively identify risks prior to Milestone (MS) decisions and other key events.  Air Force Instruction (63-101/20-101), Integrated Life Cycle Management, paragraph 3.10.1, states "The PM shall pursue a comprehensive integrated risk analysis throughout the life cycle and shall prepare and maintain a risk management plan."  The PSR process overall, which is based on an integrated, risk-centric approach is intended as a tool to assist the Program Manager (PM) in launching and sustaining high confidence programs.  The PSR process (both the assessments and outbrief) addresses any current risks regardless of how they are identified.

  - The Program Sufficiency Review (PSR) process may be directed by a Program Executive Officer (PEO) on any acquisition category programs to support any MS or other decision point.  In order for a review to be considered a PSR, it must follow the process outlined in this document.

  - The PSR assessments include:

    - Manufacturing Readiness Assessment (MRA)

    - Technology Readiness Assessment (TRA)

    - Air Force Systems Engineering Assessment Model (AF SEAM)

    - Logistics Health Assessment (LHA)

    - Risk Identification:  Integration and -Ilities (RI3) tool

  - The series of synchronized and integrated assessments identified in section 1.2 are conducted by a program office with the assistance of functional tool owners and Subject Matter Experts (SMEs) who have technical expertise in areas such as avionics, airframes, information systems, fuses, sensors, rocket motors, engines, etc.  Each program office Chief Engineer shall support all the individual assessments to ensure integration of information and results.  The findings from the assessments are used to inform the CER panel to ensure adequate resources are included in the Program Objective Memorandum (POM) submissions.  The local Cost Chief or designee will approve the annual cost estimate in support of the PSR.  In all cases, the Cost Estimate Review (CER) will be accomplished prior to convening the PSR outbrief.

  - The culmination of the program office assessments and independent SME reviews and the CER findings are briefed to a panel consisting of the PEO or designee and the appropriate level Senior Functional PSR Panel (SFPP) members.  The PSR briefing is chaired by the PEO or his/her designee.    The anticipated output of the PSR is a decision by the PEO that the program is sufficient (resources and funding) and to either continue as planned or proceed with modifications. The PEO alone has this authority.

- Purpose

  - The purpose of the PSR is to ensure that high confidence, sustainable PBs are validated and established.  A PSR provides leadership with independent objective information which can be used to support program decisions, establish executable budgets, and proactively identify risks prior to Milestone decisions and other key events.  The PSR is envisioned to support milestone decisions, program breach assessments, and re-baselining.

- Entrance/Exit Criteria and Inputs/Outputs

  - Entrance Criteria.  The Program Executive Officer (PEO) may direct the PSR process for any ACAT level and the support any MS or other decision event events including independent technical risk reviews under Better Buying Power 3.0 initiatives. Typical PSR trigger events include:

    - Initiation of a new or Preplanned Product Improvement program

    - Acquisition Milestone Decisions

    - Program re-baselining

    - Program Objective Memorandum (POM) submission

    - Acquisition Strategy Panel (ASP)

    - Responses to “what if” drills

    - Risk planning for new significant or increased program risk

  - Exit Criteria

    - PEO determination that the program is sufficiently funded and resourced

    - Any directed modifications/action items are captured, assigned and completed

  - Inputs.  The PSR uses standard assessment tools, training and processes, current program documentation and, when available, results of previous assessments.

  - Outputs.  The PEO will provide the PM with his or her approval to continue with the recommended program or proceed with modifications.  In addition, the PMO will record PSR meeting minutes, including any action items generated.  The PMO will monitor PSR action items to closure.  All action items generated during the PSR will include a date for closure and a point of contact.  Once the action items have been completed, the PMO will prepare an executive summary of the PSR outbrief.  The PMO will coordinate both the minutes and the executive summary (using examples obtained from the ACE) with the SFPP, delegated chair and designated functional staff before submittal to the PEO.  The PMO will notify the SFPP and delegated chair of the PEO’s approval to proceed or direction to modify.

- Process Workflow and Activities

This section provides a visual representation of the PSR process with details of workflow and activities.  It lays out the process from end-to-end and describes interaction between AFLCMC organizations, as well as external organizations integral to the process.

  - Supplier, Inputs, Process, Outputs, Customer (SIPOC), Table 1.

Table 1.  SIPOC

| Supplier | Inputs | Process | Outputs | Customer |
| --- | --- | --- | --- | --- |
| PEO, PMO, independent SMEs, integrated assessment tool owners, Other assessment tool owners, if included | Training Technical, programmatic and cost documentation Assessment tools Previous assessments and past SME recommendation | Execute and document a program-specific PSR Execute assessments and conduct risk workshop Conduct CER Briefing to PEO, or designee, and SFPP to assess and ensure program sufficiency | Agreement on program sufficiency to continue as planned or proceed with modifications Action items, including Plan of action and milestones (POAM) Executive summary, minutes | PMO PEO SFPP |

  - PSR Process Flowchart.  The process flowchart, Figure 1, represents the PSR process.  The activities are further defined in paragraph 4.3 below.

  - Work Breakdown Structure (WBS).  The WBS Table 2 provides additional detail for the activity boxes in the above flowchart.  The MS Excel version of the WBS with more detail is included at Attachment 1.

  - Work guidance package, additional work tables, figures, or checklists. N/A

Figure 1.  Process Flowchart – Program Sufficiency Review (PSR)

Table 2.  PSR Work Breakdown Structure (WBS)

| Lvl | WBS | Activity | Description | OPR | Days |
| --- | --- | --- | --- | --- | --- |
| 1 | 1.0 | Conduct PSR | PMO, tool owners, and their teams conduct the PSR process. |  | 180 |
| 2 | 1.1 | Initiate the PSR and corresponding planning | Trigger event and other events as requested by PEO. PMO PSR lead contacts the local Acquisition Center of Excellence (ACE) to request kick-off meeting. PMO PSR lead requests PSR tool owner contacts and briefing templates from the local ACE and conducts kick-off meeting. | PM | 20 |
| 3 | 1.1.1 | Request tool owner and technical SME support | PMO contacts tool owners and requests independent SMEs from functional directorates (may also request independent SME support from within their own directorate). | PMO | 5 |
| 3 | 1.1.2 | Conduct kick-off meeting | PMO prepares agenda, notifies attendees (PMO, SMEs, ACE) and prepares program-specific briefing (from kick-off meeting template). ACE hosts kick-off meeting and provides PSR process overview briefing. | PMO | 5 |
| 3 | 1.1.3 | Gain tools access | PMO acquires tools and processes for LHA, AF SEAM, MRA, TRA, RI3 and CER) and assessment process information from tool owners. | PMO | 5 |
| 3 | 1.1.4 | Take tool training | PMO personnel and independent SMEs receive training in tools/processes from tool owners for the selected integrated assessments. | PMO | 5 |
| 2 | 1.2 | Conduct Assessments and Cost Analysis | PMO office assisted by independent SMEs and tool owners, as requested, conduct assessments, and determines the revealed risks and cost. | PMO | 135 |
| 3 | 1.2.1 | Conduct Integrated Assessments | PMO office, assisted by independent SMEs and tool owners, conducts assessments (LHA, AF SEAM, TRA, MRA) to identify risks and suggest mitigation plans. Assessments can be conducted in parallel depending on personnel availability. | PMO | 80 |
| 4 | 1.2.1.1 | Conduct LHA | PMO personnel follow LHA process and conduct assessment. | PMO | 10 |
| 4 | 1.2.1.2 | Conduct MRA | PMO personnel follow MRA process and conduct assessment. | PMO | 80 |
| 4 | 1.2.1.3 | Conduct TRA | PMO personnel follow TRA process and conduct assessment. | PMO | 80 |
| 4 | 1.2.1.4 | Conduct AF SEAM | PMO personnel follow AF SEAM process and conduct assessment. | PMO | 45 |
| 4 | 1.2.1.5 | Conduct RI3 | PMO personnel follow AFLCMC RI3 process and conduct assessment. | PMO | 30 |
| 3 | 1.2.2 | Review assessment results (LHA, MRA, TRA, AF SEAM) | Independent SMEs review and validate assessments (LHA, MRA, TRA, AF SEAM, and RI3). PMO and cost estimate review SME recommendations and document concurrence or non-concurrence rationale for outbrief. | SMEs, PMO | 10 |
| Lvl | WBS | Activity | Description | OPR | Days |
| 3 | 1.2.3 | Consolidate Risks from all assessments and other risk identification methods (if used) | PMO consolidate risks in risk tracking tool. Assign POCs. | PMO | 5 |
| 3 | 1.2.4 | Conduct Risk Workshop | Conduct Risk Workshop using AFLCMC Risk and Issue Management in Acquisition Program Standard process (A06) and initiate/continue risk management. The risk workshop will identify risks not covered in the PSR assessments, rate the risks, assign ownership, and provide information about the risks that is useful to the cost estimators. The local ACE will facilitate Risk workshops and for ACAT I programs and pre-award ACAT II and III programs. | PMO | 10 |
| 3 | 1.2.5 | Conduct Cost Estimate Review for the acquisition program | FZC Center Staff Analyst conducts an independent assessment of the cost estimate and documentation. The Cost Chief reviews IAW AFLCMC Process Standard on Program Office Estimates’ WBS items 1.4.3-1.4.4 | AFLCMC/FZC | 30 |
| 2 | 1.3 | Provide PSR Results | Prepare and outbrief PSR results to PSR SFPP. Resolve issues, prepare executive summary, and coordinate with PSR SFPP and delegated Chair before submitting to PEO for approval. PM sends executive summary to PEO and SFPP. | PMO | 25 |
| 3 | 1.3.1 | Outbrief PSR | Prepare PSR charts using PSR standard template. Identify co-chairs (See section 6), schedule briefing, and invite SFPP members, PEO, SMEs and PMO personnel. Conduct outbrief. Take action items, and minutes. Resolve action items, or include plan to resolve in executive summary. If actions items result in significant re-work, schedule a “delta” PSR outbrief allowing time for re-work. Conduct a “delta” PSR outbrief. | PMO | 10 |
| 3 | 1.3.2 | Prepare minutes and executive summary | Prepare minutes and executive summary including action Item status and POAM (if required) for functional coordination. | PMO | 10 |
| 3 | 1.3.3 | Obtain PEO Approval | Submit coordinated minutes and executive summary to PEO for approval and sufficiency determination. | PMO | 3 |
| 3 | 1.3.4 | Document Minutes and Executive Summary | Document approved minutes and executive summary as an official record and provided copies to the outbrief attendees. | PMO | 2 |
| 2 | 2.0 | Support from Technical SMEs | Technical SMEs provide support and oversight as needed during assessments, risk workshop and at outbrief (activities are periodic and concurrent with many 1.0 sub-activities). | SMEs | 120 |

- Measurement

  - Process Results.  The PSR process improves the PM ability to more accurately plan and establish a sustainable PB.  However metrics are not required for internal process guides (IPG) and collection of PSR metric data was suspended in 2016 when this document was redesignated as an IPG.

- Roles and Responsibilities

  - PEO

    - Assess and determine necessity for a PSR at triggers in 3.1.

    - Chair (or assigns designee) PSR briefing.

    - Direct 2-letter Organization Senior Functionals to identify independent SMEs for   ACAT II, ACAT III.

    - Approve omission of specific assessments prior to PSR Conduct.

    - Assign 2-letter organization Senior Functionals to the ACAT II or III program SFPP, or request Center level office(s) assist in identifying SFPP member.

    - Provide PM with determination of sufficiency to continue or direction to modify the program.

  - AFLCMC/AQ-AZ (ACE) (Process Owner)

    - Maintain and coordinate any changes to the PSR process.

    - Ensure PMO point of contact understands the responsibility of the program office to prepare for PSR kick-off meeting.

    - Identify tool owners and provides technical SME recommendations.

    - Host PSR kick-off meeting (once requested by the PMO).  Assist as requested throughout the PSR process for ACAT I and pre-contract award ACAT II and III programs.

    - Request and coordinate SFPP support for ACAT I PSRs.

    - Submit electronic ACAT I PSR brief (from PMO) to SFPP prior to PSR.

    - Maintain a PSR Sharepoint site with templates for briefings, post out-brief documents and lessons learned.

  - AFLCMC/EN-EZ

    - Develop and maintain the AF SEAM, MRA, TRA, RI3 process, tools, and guidance.

    - Develop and provide training for the AF SEAM, MRA, TRA, and RI3.

    - The AFLCMC/EN-EZ Director, or the Director’s designee leads the independent technical expert team of SMEs for ACAT I, or non-delegated ACAT II programs, and ensures Overarching Integrated Product Team (OIPT) and subsequent submittals of the independent technical risk review are accomplished.

    - Provide independent SMEs for ACAT I programs and when requested other ACAT programs, or work with the Directors of Engineering or other organizations to obtain SMEs.

    - Support local independent SME assignments; otherwise provide SME if no local SMEs are available.

  - AFLCMC/FM-FZ

    - Maintain and coordinate any changes to the Annual Program Office Estimate (POE) process.

    - Approve/disapprove annual estimate in support of PSR.

    - Develop and provide training for the CER.

    - Provide independent SMEs when requested.

  - AFLCMC/LG-LZ

    - Maintain and coordinate any changes to the LHA process.

    - Develop and provide training for the LHA.

    - Provide SMEs when requested.

  - PEO’s Director of Engineering

    - Inform PEO when policy requires an independent technical review on a program.

  - Program Manager

    - Initiate kick-off request with the local ACE (AFLCMC/AQ-AZ).

    - Designate a PMO PSR lead and provide functional team (e.g., engineering financial management, program management, contracting, and logistics) to conduct the integrated assessments, risk, and cost estimating activities to support the PSR.

    - For ACAT I programs, request independent SMEs from Center level offices.

    - Develop and coordinate PSR schedule with tool owners and independent SMEs.

    - Ensures the PMO representatives for each integrated assessment collaborate across the assessments.

    - Ensure coordination of findings and recommendations between the Chief Engineer, Cost Chief, and SMEs.  Include SME findings in the PSR outbrief.

    - Develop PSR outbrief and coordinate with independent SMEs.

    - Provide electronic copy of PSR outbrief to ACE.

    - Host PSR, develop, coordinate, and distribute the meeting minutes and executive summary. Document PEO’s rationale for non-concurring with SFPP recommendation, if not accepted.  Track and facilitate action item closure.

  - PMO PSR Lead

    - Contact the ACE for assistance identifying the tool owners and to correctly apply the latest version of the tools.

    - Consult with the appropriate tool owner for their determination on whether an assessment may be tailored or omitted for a specific PSR.

    - Request PEO approval for omission of any assessment. If assessments are omitted or tailored, the rationale will be formally documented and presented at the PSR outbrief

    - Act as the PM’s agent to implement his responsibilities as requested.

  - Senior Functional PSR Panel (SFPP)

    - Support the PSR process when requested. For ACAT I programs the SFPP will be comprised of the Center Senior Functionals. Site Senior Functionals may also be requested to attend. For ACAT II and III programs the PEO’s Senior Functional Staff shall serve on the SFPP unless the PEO requests a Center functional representation. SFPP members ensure the technical integrity and the independency of the review of assessments in their functional areas.

    - Review read-ahead charts. Work any issues ahead of time with the PMO, if possible, to minimize discussions at PSR outbrief.

    - Assign a representative to attend PSR outbrief in the case of schedule conflicts.

    - Receive PSR outbrief and provide input/suggestions as appropriate.

    - Provide recommendation(s) to PEO for final decision.

- Tools

  - PSR SharePoint Site can be accessed from the AFLCMC ACE community page:

https://cs.eis.afmc.af.mil/sites/ASCACE/default.aspx

  - SMART (LHA) - The Acquisition Workbench is used to perform the Logistics Health Assessment (LHA).  Initial online training must be completed before access will be given.  For access and training please contact the System Metric and Reporting Tool (SMART) Helpdesk at 888-925-4561.

https://af-aqweb.deps.mil/Pages/Default.aspx

  - AF SEAM, TRA, RI3 and MRA Guidance /Tools (AFLCMC/EN-EZ SE Tool Set) https://cs.eis.afmc.af.mil/sites/AeroEngDisciplines/Systems/SETools/default.aspx

  - Probability/Consequence Screening Tool

https://cs.eis.afmc.af.mil/sites/ASCACE/pages/PCS%20Tool.aspx

- Delivery Approach

  - Just-in-time Training

    - AFLCMC/AQ-AZ will provide PSR process overview training prior to or at the PSR kick-off meeting.  ACE facilitates Risk Workshop training is also provided.

    - AFLCMC/EN-EZ tool owners will provide AF SEAM, MRA, TRA and RI3 training prior to programs conducting the individual assessments, if necessary.

    - AFLCMC/FM-FZ will provide CER training, if necessary.

    - AFLCMC/LG-LZ will provide LHA training, if necessary.

  - General Awareness Training – The process owner will provide bi-annual Focus Week training on PSRs on-site at WPAFB and via distance learning at other operating locations.  Training will also be provided on request.

- Definitions, Guiding Principles and/or Ground Rules & Assumptions

  - In order to be considered a PSR, the activities must follow this process guide.

  - Functional staffs develop and maintain individual assessment tools and processes.

  - The Senior Functional PSR Panel (SFPP) is Chaired by the PEO or his/her designee and includes, as a minimum, senior functionals in engineering, finance, logistics, program management contracting, and for ACAT I’s, Acquisition Excellence. Senior Functionals from test, intel and others are included if appropriate for the program.

- References to Law, Policy, Instructions or Guidance

  - AFI 63-101/20-101 Integrated Life Cycle Management, IC2 23 Feb 15, requires programs to assess and mitigate risks of all kinds as a routine part of program management and to clearly identify risks during program reviews.

  - AFI 65-508 Cost Analysis Guidance and Procedures, 06 June 2012.  POEs are governed by AFI 65-508 and are required for all ACAT I, II and III programs to be updated annually, unless waived.

  - AFLCMC Process Standard B02,  Annual Program Office Cost Estimate, 4 Feb 2016

  - AFLCMC Process Standard A06, Risk and Issue Management in Acquisition Programs, 10 Jul 2015

Attachment 1:  MS Excel WBS

PSR full WBS 1

# Text boxes

Air Force Life Cycle Management Center (AFLCMC)

Internal Process Guide

to

Conduct Program Sufficiency Reviews (PSR)

Process Owner:  AFLCMC/AQ-AZ

Date:  8 March 2016

Version: 1.0