## Slide 1
Box used to identify where SSRA and ESC should be considered
Purple text used to add considerations for SSRA and ESC:
    Spectrum Supportability Risk Assessment Status
    Equipment Spectrum Certification Stage
    DoDI 4650.01 page 12 covers Spectrum Supportability Risk Assessment. Consider Spectrum Supportability Risk Assessment Status:
    Equipment Spectrum Certification Stage

## Slide 2
Rank, Name
Office Symbol
Date of Briefing
Version #
Updated: March 19
This template is for guidance
and is not mandatory
Middle Tier of Acquisitions (MTA)/Section 804
Acquisition Strategy Panel (ASP) Template
Please refer to the notes section for valuable guidance
Additional MTA/SECT 804 Guidance/Information located at Secretariat SharePoint:
https://cs2.eis.af.mil/sites/10263/dir/integration/execution/Secretariat/Forms/AllItems.aspx

## Slide 3: Outline
Bottom Line Up Front (BLUF)
Program Structure
Factors Shaping Strategy
Acquisition Strategy
Product Support Strategy
Business Considerations
System Engineering
Test & Evaluation
Guardrails
Documentation Plan
What Worries Me
Recommendations
Back-Up
    MTA Data Elements Charts
ASPs scheduled for 1 hour
Goal should be to present ~30-35 charts
Notes: AFI 63-101, 20-101, Para 3.6.2.2 requires that “ASPs shall be held for all ACAT programs that are presenting a new strategy or a significant revision to an approved strategy. The Acquisition Strategy (document) still requires approval by the MDA.”
This template is designed as a “guide” through the myriad of topics and issues that may need to be addressed in developing and presenting an acquisition strategy. EACH STRATEGY SHOULD ONLY ADDRESS THOSE TOPICS THAT APPLY, BUT BE PREPARED TO ADDRESS ALL ACQUISITION STRATEGY TOPICS!
The basic goal is to provide the decision maker an understanding of a well thought out strategy that considered all important issues
See OSD AS Template at the ACE website for guidance on requirements for the written document.
Information is contained in the notes section of each chart to help you in preparing the briefing.
Sample charts are provided in back-up. With the exception of the funding and logistics charts; if the charts are not appropriate for your presentation alternate charts should be used.

## Slide 4: Bottom Line Up Front (Decisions Requested & Key Program Info)
Decisions Requested
  Approve Designation as MTA/Section 804
  Approve Acquisition Strategy (see notes)
  Approve Applicable delegations/waivers (e.g., Source Selection Authority)
Issues/Concerns
  List “show stoppers”
  What are your concerns?
  See Notes page for additional information
Notes: This chart sets the stage for decisions the ASP Chair will have to make as well as to identify key issues to the ASP panel that may impact the strategy.
As an example--are you requesting any delegations or approvals?
  J&A approval
  SSA Source Selection Authority delegation
  Clearance Review and Approval Authorities
While it is not mandatory, nor possible in one hour to address all the subjects, it is prudent of the briefer to be able to address and brief all topics including those in the back-up portion of this Template and the OSD AS Template.
For additional information review the OSD AS Template at the AECO Secretariat website https://www.my.af.mil/gcss-af/USAF/ep/globalTab.do?channelPageId=s6925EC13430A0FB5E044080020E329A9&pageId=681742.

## Slide 5
Decision Authority
MDA:
PEO Program: (AFPEO/XX)
ACAT Level:
SSA:
Delegations: (SSA, ASP Chair, LCMP, etc)
Strategy
Competitive or sole source:
Contract Type:
Estimated Contract Award:
Schedule: (MS A, MS B, IOC)
Program Structure
Financial Data
Est. Contract Value (Pre-EMD):
Est. Total Program (qty):
Fund Type (Pre-EMD):
New Start (Congressional):
Requirements/Direction
Using Organization(s):
Capabilities Document: (ICD, CDD, CPD)
Joint requirement:
FMS:
Technical Risk:
ADM:
Notes: A good early chart is this quad chart. It provides the “strategy on a page” for the panel It can be a series of one-liners—some of the topics that could be included are:
  What is being acquired (hardware, SW, etc.)
  Is this satisfying a joint requirement?
  Whether effort is a mod, foreign procurement, cooperative development, new US development, or foreign military sale (FMS)
  ACAT level
  Whether strategy is incremental or single step
  Entry point (MDD, MS A, B,C)
  Whether competitive or sole source
  Whether there will be successive down selects or re-competitions
  Overall technology assessment
  Overall Risk level
  Next major activity
  Funding status
  New development

## Slide 6: Program Schedule
MS C
Development
MS B
LEGEND
Program Milestone
Gov’t Milestone
FY:
PRODUCTION
EMD
IOC
(6/6)
CT&E
FRP
DT&E IOT&E
LRIP
# of items
# of Items
FRP
2014
2015
2016
2017
2018
2019
2020
2021
2022
2023
2024
2025
ICD
CDD
CPD
Capabilities
Documents
2026
Tech
Demo
Milestones:
Concept
Decision
MS A
CDR
RFP Rel
DSOR
Logistics
PDR
IBR
ED Guidance
Depot
Activation
Major Contract
Events
CA
Development RFP
Review
Time Now
Discuss MTA/Sect 804 Transition Strategy
Consider SSRA (regulatory) and ESC (statutory) status.
Notes: As a reminder this schedule is generic. Other examples of Schedules could be Systems Engineering, Test Events (from the OSD AS Template page 6). As an example it depicts testing to show the goal of a integrated DT and OT testing. Normally IOT&E testing is accomplished using LRIP items. IOT&E cannot be done using a prototype unless the OT&E (DOT&E with MDAP) approves. An alternate schedule might show the integrated goal as using DT&E/OA (operational Assessment) than a short IOT&E. Normally the schedule should show key acquisition decision points; principal systems engineering and logistics activities such as technical reviews and assessments; planned contracting actions such as request for proposal (RFP) release, source selection activity, and contract awards; production events and deliveries; and key test activities. Good chartsmanship would include a doted line indicating where we are today!!
Identify Major Schedule Drivers: e.g., Obsolescence? Are we trying to beat someone in this competitive space and what’s the value proposition for doing so?
What technical issues pace the project?

## Slide 7
Summarize Benefits/Impacts
Initial capability available 3 years earlier…
FY18 |  |  |  | FY19 |  |  |  | FY20 |  |  |  | FY21 |  |  |  | FY22 |  |  |  | FY23 |  |  |  | FY24 |  |  |  | FY25 |  |  |  | FY26 |  |  |  | FY27 |  |  |  | FY28 |  |  |  | FY29 |  |  |  | FY30 |  |  |  | FY31 |  |  |  | FY32 |  |  |  | FY33 |  |  |  | FY34 |  |  |  | FY35 |  |  |  | FY36 |  |  |  | FY37 |  |  | 
5000.02 Program
Section 804 Activity
TMRR
ATP
PDR
SRR
SFR
SS
ASD/RFP
ATP
CDR
EMD
Production
MS-A
MS-C
CDD-V
dCDD
MS-B
DRFPRD
Rapid Prototyping
Spiral Decision
Development Spiral/
Production Decision
Production Decision
Traditional vs MTA
Schedule Benefit
Rapid Prototyping Spiral
PDR
CDR
SVI&T
Development Spiral
PDR
CDR
SVI&T
Production/Fielding
ΔCDR
4
5
6
7
8
9
3+ years
Continuous Technology Insertion/Innovation

## Slide 8: Factors Shaping Strategy
Discuss Capability Required
  Effect of Capability & Gap it will mitigate
  CONOPS, OV-1
  Key Performance Parameters (KPPs) & Key System Attribute (KSAs)
  Reliability, Availability, Maintainability Requirements
  Acquisition Approach
  Collaboration accomplished in developing capabilities
Has industry been involved? Have they influenced requirements?
    Identify requirements Industry has indicated they can’t meet either in capability document or affordability goal
See notes
Notes: Consider having a senior “warfighter” as briefer to provide more insight into the User’s needs and wants.
Capability/Requirement: Do you clearly understand the requirement/capability needed? Is it realistic? Are the requirements defined in increments that can be achieved in a EMD phase of 5 years or less? If not, explain why we are pursuing requirements that will result in a longer EMD phase. Identify all KPPs. Do you and the operator have the same understanding of the requirement? Identify the top KPPs or KSAs that are driving program costs to meet operational requirements.
Reminder that “All acquisition programs will coordinate the requirements document used in conjunction with a RFP with the requiring Lead Command prior to the release of the final RFP.” (AFI 63-101_20-101, para 7.1) Identify either here or in the schedule when that will happen. Was the Program Office a part of the requirements development process?
If you have an ICD, how/when will the CDD be completed, likewise a CDD to a CPD or CDD to the next CDD if evolutionary in nature. For a MAIS program, address the applicability of a CPD when there is no "production"; address any agreement with the users regarding applicability of a CPD.
  Other topics to address as appropriate:
    Jointness
    Is AoA, CONOPS complete; other alternatives considered (DOTMLPF)
    Does the document identify incremental requirements
    Need dates per increment
    Consider Spectrum Supportability Risk Assessment Status and Equipment Spectrum Certification Stage and their impacts to the process/strategy

## Slide 9: Factors Shaping Strategy Affordability Requirement
Affordability goals
  Do you have enough information to develop an affordability goal?
  Using both average unit acquisition cost & average annual operating & support cost per unit what will you be able to present at MS A/B event?
Strategy for achieving this “KPP”-like topic
  Identify specific contract provisions (e.g., Goals & Incentives in RFP)
  Identify changes to quantities such as EOQs that are necessary to achieve target
  Identify schedule changes necessary to achieve goal
Impact of procurement rate (EOQ) & schedule on affordability goal
Affordability Requirement Source
Notes:       Several points--
  --The affordability goal should be presented in the context of an analysis of the resources that are projected to be available in the portfolio(s) or mission area(s) associated with the program
  --In order to meet this requirement, you will need to provide a quantitative analysis of the program's portfolio or mission area across the life cycle of all products in the portfolio or mission area, including acquisition and operating and support budget suitability to absorb the proposed new start as a content change.

## Slide 10
Affordability Goals
Cost Drivers & Trade Excursions Plan
Affordability Caps:
Notional System
Description | Cost Target
APUC | $27.8M
O&S | $40.3B
Description | Trade Excursion | Date
- Range Readjustment | Speed/Range Tradeoff Review | 2Q FY11
- Reliability Growth | RAM Study | 3Q FY11
- Engine Redesign | NAVAIR /CTR Focus Group | 3Q FY11
- Prognostics & Health Mgmt. | Independent Logistics Assessment | 3Q FY12
- F/A-XY Avionics Reuse | NAVAIR Tiger Team | 3Q FY12
- Reduced Ordnance Load | JROC Review | 4Q FY12
Indicate Source of Affordability Cap
Notes: Affordability Template MS A (Single Quad-Chart)
Purpose: Provide an overall context of the proposed system Affordability Goals within the Portfolio/Mission Area (P/MA).
Top left quadrant: Display proposed Affordability Goals for MDA approval as a table. First column is a description of the affordability factor (usually PAUC, O&S or another major cost element, but may also be manpower, fuel, or other sub-element if appropriate). Second column is a target cost that will serve as a not to exceed as the program continues to MS B. Except for exceptional circumstances this cost should be no more than 3 significant digits.
Top right quadrant: Provide description of expected Affordability Drivers and plan of action to conduct engineering cost and schedule excursions, and to incrementally review cost and schedule trades to improve affordability. Dates should be completion dates, after which the results can be provided during program reviews.
Bottom:
Discussion points.

## Slide 11: Factors Shaping Strategy: Cost Capability Analysis
Discuss what is included in acquisition strategy to help find right balance between operational capabilities & affordability
  How will acquisition strategy examine trade space between operational requirements & cost?
  Discuss plan for conducting cost capability analysis during Risk Reduction to identify opportunities to trade off operational capabilities to achieve a more affordable program
    Which requirements are most costly &/or risky?
    Which requirements could result in cost savings if adjusted?
    Where is knee in cost capability “curve” for most costly or risky requirements?
  How do you plan to engage with industry to get their understanding of how requirements might be traded to make program more affordable?
Focus is on Risk Reduction
Notes: Cost Capability Analysis is used to help identify operational requirements and is required to be reported at acquisition and requirements forums IAW AFI 10-601 and AFI 63-101. See backup slide for example trades worksheet.

## Slide 12: Factors Shaping Strategy: Program Cost Estimate/Funding
Identify cost estimate & methodology
  Confidence level (55-80%)
  LCC estimate (product support %)
Program Office Estimate or Service Cost Position?
Address any AFCAA/OSD CAPE issues that may exist
Address funding shortfalls
  Explain budget plans
  RDT&E plan for executing obligations & expenditures
  Explain MAJCOM commitment to cover shortfall as applicable
*See Notes Page
Proffer a fully funded Acquisition Strategy
  See Notes Page
Notes: The acquisition strategy shall address the estimated program cost and the planned program funding, including advanced procurement funding.
Cost Estimate--Identify the cost estimating methodology used to estimate major program cost drivers (parametric, cost estimating relationship, analogy, engineering build-up, EVM data, etc.)
  Identify if any data was contractor provided as in a response to an RFI
Address any funding issues/disconnects, to include phasing/types of funds. Explain your work around plans to continue performance. How does this impact risk? What are MAJCOM commitments to supporting the program in the out-years?
  AF requires that programs address sequestration and known shortfall by proposing “what the program would look like with available funding
OSD requires ACAT I programs to be fully funded.
  If there is a funding mismatch, the PM should present a fully funded program at the “disconnect number.”
  If an evolutionary approach is being used fully fund 1st increment of capability. Funding of subsequent increments should be discussed.
  Is the program funding currently supported in the President’s Budget?
  Identify the percent of the estimate associated with providing for product support

## Slide 13: Funding Profile
Chart is Mandatory
Notes: Notes:
+Enter values in the unshaded (white) annual and to-complete cells only. The rest of the data is calculated automatically. The spreadsheet cells will round to the nearest hundred thousand dollars ($0.1M).
+Delete any appropriation sections that have no budgeted or required costs.
+Programs must use footnotes to state source of "Required" estimate, O&S service life projection, O&S time horizon (first year of O&S – last year of O&S) & cost categories, and any RDT&E-funded quantities (if any). See Figure 1.
+Program offices are to use the latest version of the program funding template. Regularly check the Acquisition, Technology and Logistics (AT&L) Defense Acquisition Board (DAB) online calendar website (https://ebiz.acq.osd.mil/DABCalendar/) for the most current Integrated Product Team (IPT) Program Funding template. The template is updated as Programming, Planning, Budgeting, and Execution System (PPBES) events occur.
Definitions:
Primary Line Items: In the header of each section, list the primary budget line item(s) that fund the program currently and in the FYDP. For RDT&E, MILCON, and O&M, include appropriation (consistent with DAMIR reporting), budget activity and program element. For procurement, include appropriation, budget activity and line item. Some programs have smaller amounts of funding in secondary line items that need not be listed. Footnotes may be used for clarification/amplification.
Prior: President’s Budget (PB) position submitted prior to the Current budget position. Although the President only submits the FYDP to Congress, the cells for the next fiscal year and “To-Complete” should be populated for the investment appropriations using the values reported in the Selected Acquisition Report or latest DAES associated with that PB (if available).
Current: Latest approved Service POM/BES budget position or approved PB.
+During a normal PPBES cycle (PB submitted in the first Tuesday of February each year), use POM position from August through January; Use PB position from February through July.
+When the DoD Appropriation is enacted, programs should update that cell of all the "Current” PB funding and quantity rows to reflect the actual appropriated amounts.
Required: Latest estimate of funds required to successfully execute program, i.e., support the Warfighter and not simply match available budget Total Obligation Authorities (TOAs). Typically, this would reflect the Will Cost estimate, Service Cost Position (SCP), or PEO-supported Program Office Estimate (POE) that has not yet been validated by a Service Cost Agency or the CAPE. Note: total required quantity is the acquisition objective recognized by the Joint Requirements Oversight Council (JROC) or similar body and would be reflected in the program's Acquisition Program Baseline (APB) or similar document but may not be reflected in the budget due to affordability or funding issues.
System O&M: In this section, list the O&M-funded costs from initial system deployment through end of system operations. Include all costs of operating, maintaining, and supporting a fielded system. Specifically, this consists of the costs (organic and contractor) of equipment, supplies, software, and services associated with operating, modifying, maintaining, supplying, training, and supporting a system in the DoD inventory. Do not include acquisition-related O&M, and non-O&M O&S costs such as military personnel, and investment-funded system improvements. Also, do not include disposal costs, which represent a separate phase of the program life cycle. Please address questions on the O&M requirements to the OSD(AT&L)/L&MR point of contact listed below.
Total Required Acquisition (BYXX$M):
+Current Estimate of Total RDT&E, procurement, MILCON and acquisition-related O&M in base-year dollars as reported in the program's latest approved POM budget position, approved PB, or quarterly DAES submission, whichever is most current.
+The percentage displayed is the portion of the Acquisition cost out of the sum of Acquisition and O&S costs.
+Revise “BYXX$M” to reflect the 2-digit program Base Year (e.g., BY15$M). Use the Base Year specified in the current Acquisition Program Baseline (APB). For unbaselined programs (or if seeking a new or revised APB), use the budget year (e.g., BY17$M for POM-17).
Total Required O&S (BYXX$M):
+Current Estimate of Total Operating and Support costs in base-year dollars as reported in the program’s quarterly DAES (if applicable). See Figure 2.
+A footnote should identify the projected service life.
+Disposal costs should not be included in this value.
+The percentage displayed is the portion of the O&S cost out of the sum of Acquisition and O&S costs. This value should not include disposal dollars.
+Revise “BYXX$M” to reflect the 2-digit program Base Year (e.g., BY15$M, IAW the instructions above for Total Required Acquisition).
Curr Est (APUC): Program Manager’s current estimate of Average Procurement Unit Cost, in base-year dollars (total procurement divided by procurement-funded quantities). The APUC should match the values reported in the program's latest approved POM/BES budget position, approved PB, or quarterly DAES submission, whichever is most current.
Curr Est (PAUC): Program Manager’s current estimate of Program Acquisition Unit Cost, in base-year dollars (total RDT&E, procurement, MILCON and acquisition-related O&M divided by total quantity). The PAUC should match the values reported in the program's latest approved POM/BES budget position, approved PB, or quarterly DAES submission, whichever is most current.
Δ Current: This is the program’s APUC or PAUC current estimate (as defined above) divided by the program’s current APB Unit Cost Reporting (UCR) baseline, as applicable. Figure 3 illustrates where this information resides in the program’s DAMIR DAES.
Δ Original: This is the program’s APUC or PAUC current estimate (as defined above) divided by the program’s original APB UCR baseline, as applicable. See Figure 3.
Points of Contact:
Army Programs:
Allen Johnson, OSD(AT&L)/ARA
allen.m.johnson44.ctr@mail.mil
703-697-5384
Navy Programs:
LCDR Joseph Mitzen, OSD(AT&L)/ARA
joseph.b.mitzen.mil@mail.mil
703-697-8020
Air Force Programs: LCDR Joseph Mitzen, OSD(AT&L)/ARA
joseph.b.mitzen.mil@mail.mil
703-697-8020
Agency & Department-wide Programs:
Mr. Russ Vogel, OSD(AT&L)/ARA
russell.a.vogel.civ@mail.mil
703-697-1786
O&S Section:
Ms. Molly Mertz, OSD(AT&L)/L&MR
mary.m.mertz.civ@mail.mil
703-614-6137

## Slide 14
Likelihood
Consequence
Supply Chain Management to Support Increase to FRP
Driver: Poor performance of key suppliers, long lead times (bearings, forgings, castings), LLT purchase orders, staffing, parts shortages, and limited capacity in critical suppliers
Mitigation Plan:
Obtain Advanced Procurement in FY10
Hire Govt Supply Chain Manager (V-22)
Identify dual source for critical suppliers
Rationalize supply base
Place reps on-site at critical suppliers
Hire staffing to meet demand
Utilize company gated process for outsourcing
Award FY10 Long Lead
Support Prime key supplier visits with govt reps
Production Readiness Review (support FRP decision)
Date: COMPLETE Jul 10 (Risk will be closed)
Ability to Achieve Affordability Goals to Meet Inventory Objectives
Driver: Higher than anticipated costs due to enterprise growth (overhead rates); raw materials; cabin; supplier performance; increased labor hours. Two rate increases (driven by a reduction in the base vs. predictions, erosion in the commercial business, efficiencies in production, a recent strike, and pension liabilities) have recently created additional budget pressure.
Mitigation Plan:
Establish Affordability plan
Implement GFE CRIs (Engines, OTO)
Obtain Advanced Procurement in FY10
Execute Long Term Agreements/Long Term Contracts
Finalize inspection requirements
Assess impacts of PB11 Budget and rate increases with Lot 7 Production Proposal
Include spares in production contract
Complete Business Case Analysis for MYP
If supported by BCA, ensure MYP budget approval/lay-in and implement MYP to begin in FY14
Date: On-going
Failure to Meet Total Ownership Cost Reduction Goals
Driver: Delayed I and D level standup, dynamic component DL&T disposition, extended ICS, items not making reliability targets
Mitigation Plan:
Conduct BCA for long term sustainment/PBL strategy
Stand up Organic Intermediate and Depot Level repair
Approval of H-1 DL&T’s
Execute 5 year Interim Support Plan contract awards
CILR drives component redesign efforts/BCAs
Date: Ongoing
Insufficient funding to execute aircraft buys
Driver: Two Forward Price Rate Agreement (FPRA) increases (driven by a reduction in the base vs. predictions, erosion in the commercial business, efficiencies in production, a recent strike, and pension liabilities) and potential additional rate impacts due to Pension Protection Act compliance and projected business base loss in FY14 due to fewer aircraft buys are creating budget pressure to execute yearly budgeted a/c quantities and pressurizing APB and Nunn-McCurdy acquisition thresholds.
Mitigation Plan:
Finalize technical evaluation and negotiation
Assess future rate increases and impacts on FYDP(ongoing)
  Pension Protection Act assessment (AIR 4.2 Lead)
  Business base (DCMA lead)
Continue to Pursue cost reduction/control initiatives
Update program manager’s cost estimate
Engage Service for funding resolution
Support PEO(A)/DCMA rate control initiative with company
Date: Oct 10 (FRP decision)
See Notes Page
& Backup Chars
Program Risks
Notes: 14
14
  Identify the key Programmatic Risks—Cost, Funding, Schedule, Performance (Technology, Software, Manufacturing, Supportability, Industrial Base, Manufacturing, Political).
  What are they? Why do you think they are the only ones?
  How are you going to address them?
As an example have you evaluated/identified potential risks such as:
  --Technology: TRL level for critical technologies which may impact meeting a KPP, KSA, or APA thresholds or represent risk to deliver capability on schedule and budget, software, interoperability, integration, certification, interface with other systems, Safety, ESOH, Hazards
  --Testing: aircraft availability, Software Integration Lab (SIL) availability
  --Program Office: Lack of trained personnel, insufficient manpower
  --Intelligence support as is relates to cost, schedule and performance
  --Manufacturing: Are Mfg processes in place & compliant to their established procedures/processes? Are contractor’s capable of delivering on time?
Describe mitigation plans for all red and yellow risks in the backup charts
  Mitigation Plans should be realistic and descriptive.
  The purpose of the mitigation plan is to describe how this particular risk will be handled – what, when, by whom and how will it be done to avoid or minimize consequences. . A good plan should contain a schedule for implementation, with an OPR.
  Examples of risk mitigation efforts include reducing software development risk by developing and delivering software incrementally, prototyping, simulation, alternative designs, additional resources (earlier engineering involvement, additional engineers), workarounds, etc.
  DOD Risk guide: http://www.dau.mil/publications/publicationsDocs/RMG%206Ed%20Aug06.pdf

## Slide 15: Acquisition Strategy SAMPLE Framing Assumption #1
Expectations
Implications
Framing Assumption
Purpose-built will be competitive with existing designs
Basic aircraft and training system designs will be complete through vendor-conducted CDRs
Enter at MS B
Limited EMD of “deltas” to meet spec
PDR and competitive prototype waivers applicable*
Best-value source selection must consider risk
Contractor flight data to validate performance
Single step to full capability
Single award for EMD, Prod and ICS
RAA in 2023
FOC in 2031
*Air Force will still conduct comprehensive PDR and Critical Design Review (CDR) events post-contract award in support of Better Buying Power (BBP) 3.0 “Strengthen organic engineering capabilities” and SAF/AQ’s OTB Initiative.
See Notes Page
Notes: *The PM and team should develop the programs Framing Assumption and track the validity of the FAs by assessing relevant program metrics.
**Show implications, expectations and metrics for each key framing assumption. There should only be a few FAs (3-5); each should have these properties, cause major consequences, have no simple work-around, be uncertain at this point, be program specific (not generic, lie funding stability or good contractor performance ) and be a fundamental assumption that affect management decisions.
***Describe the visible expectations that flow from each implication of the FA.
****Specify metrics that can show whether these expectations are seen
Examples of Framing Assumptions:
  Adequate industrial base for competition
  Technology well in hand
  Requirements achievable
  Aggressive schedule is risky but achievable
  SPO will have personnel to handle integration role
  “Back to basics” would help solve technical and mgt issues
  Separate space and ground segments would provide “best of breed”
  Incremental/block approach
  Capability Insertion Program, graceful growth
  Incentivize for mission success, on-time/on-cost delivery, high confidence approach

## Slide 16: Acquisition Strategy Sample Framing Assumption #2
Expectations
Implications
Framing Assumption
APT
requirements only
Mature technologies and systems available
Single step, limited EMD, waivers etc.
AETC sole customer
Separate PPBE
process for
other T-38 owners
Separate Planning Programming Budgeting and Execution (PPBE) process for APT derivative use capabilities
IOC 2023
See Notes Page

## Slide 17: Acquisition Strategy Alt Sample Framing Assumptions
Assumption* | Implications** | Expectations*** | Metric****
Design is Mature | Production concurrency possible | Schedule to IOC will be achieved | Schedule growth below historical median
Threat levels will not change much in the next 5 years | Capability changes unlikely | Costs to stay on track | 
Commercial demand will reduce unit cost | Production cost Est is realistic | No additional funding needed nor cost growth | 
Schedule Incentive will motivate Ktr | Schedule will be achieved | Warfighter IOC date will be met | 
See Notes Page
Notes: *The PM and team should develop the programs Framing Assumption and track the validity of the FAs by assessing relevant program metrics.
**Show implications, expectations and metrics for each key framing assumption. Thee should only be a few FAs (3-5); each should have these properties, cause major consequences, have no simple work-around, be uncertain at this point, be program specific (not generic, lie funding stability or good contractor performance ) and be a fundamental assumption that affect management decisions.
***Describe the visible expectations that flow from each implication of the FA.
****Specify metrics that can show whether these expectations are seen

## Slide 18: Proposed Acquisition Strategy
Acquisition Strategy defines approach program will use to achieve full capability
  Should include a brief rationale to justify the choice
Summarize cost, schedule, & performance drivers under consideration, & plan to transition from MTA (Rapid Prototyping/Fielding) to DoD 5000.02 or another MTA
  Specify any unique program circumstances
  Are you replacing an existing system (modification or new capability)?
  Is this a joint program?
    Identify Service(s)/DoD Components, Service-specific technical & operational differences; roles & responsibilities, & program funding
  Address any regulatory tailoring necessary for program efficiency
  (See notes)
See Backups for sample charts on alternatives considered & rationale
for strategy selected
Notes: The Acquisition Strategy:
Guides program execution across the entire program life-cycle
The proposed strategy should cover development, testing, production, and life-cycle support
It must be flexible enough to accommodate acquisition oversight decisions both on this program and on other programs that may affect this program
It should address the availability of required capabilities to be provided by other programs
It establishes the milestone decision points and acquisition phases planned for the program
It should prescribe the accomplishments for each phase, and identify the critical events affecting program management
OSD focus is a competitive strategy throughout the life of the system
Have you considered breakout of subsystems?
DoDI 4650.01 page 12 covers Spectrum Supportability Risk Assessment. Consider Spectrum Supportability Risk Assessment and
Equipment Spectrum Certification.

## Slide 19: Competition Strategy/Market Research
  Competition Strategy
    Explain how competitive environment will be sought, promoted, & sustained throughout all program phases
    Summarize competition strategy for upcoming phase
    Where head-to-head competition is not possible, explain how dissimilar competition or other competitive approaches will be used
  Market Research
  Summarize research conducted & results. Indicate specific impact of those results on various elements of program
  Plans for continuing market research to support program throughout development & production
  Plans for getting industry insights on potential requirements & cost trade space to support AF’s cost capability analysis
  Sole Source Authority
  Identify legal authority & basis
  Planned action to obtain future competition (e.g., buying tech data package & associated intellectual property rights)
Notes: Taken from the OSD AS Template Para 7.1: Describe your contracting approach and If a source selection is required ,your best “value approach.”
Describe the source selection approach-structure, SSA, Criteria—key section L&M criteria
Describe type & number of contracts expected & why you chose that approach.
The experience of the SS team can be addressed here or in the section on program office personnel
Risk-based Source Selection. The source selection approach, as part of the acquisition strategy, shall be developed to reduce risk over the life cycle of the program. This includes identifying the strengths, weaknesses, domain experience, process capability, development capacity, and past performance for all developer team members with significant development responsibilities. This should inform key technical and appropriate program risks and the formulation of source selection evaluation criteria. Source selection guidance contained in FAR Part 15, DFARS Part 215, AFFARS 5315.3 (for Mandatory and information information).
Only use LPTA when able to clearly define Technical Acceptability.
TMRR phase: Explain strategies for working with Industry to get Industry's insights on possible requirements and cost trade space. Ideal questions for Industry: Which requirements are the most costly and/or risky? Which requirements could result in savings if adjusted and how much savings? Where is the knee in the cost capability curve for the most costly or risky requirements? The insights to the above questions will assist with informing requirements decisions based on the findings from the TMRR phase. Based on lessons learned from other programs, TMRR is the best time to have this engagement with Industry.

## Slide 20: Contract Parameters
  Contract Type
    Rationale for contract type
    What measures are in place to control contract costs?
  Describe type & number of contracts expected & why chosen—will this reduce program risk?
  Considered breakout of subsystems?
Contract Structure (Length, Options, CLINs)
Special Terms & Conditions
  Organizational Conflict of Interest (OCI), Pricing Matrix, Warranty of Data (DFARS 252.246-7001), Warranties, Advance Procurement
  If Undefinitized Contract Action (UCA) is planned, discuss rationale & get well plan
Subcontractor Management
  Make or Buy considerations
Notes: Describe the geometry of the contract type, e.g. target cost, target fee, min/max fees, share ratios, ceiling prices as applicable for the contract. If you are planning on an Advance Procurement or a UCA—it may required SAF/AQC approval
As appropriate address Shutdown costs (“tail-up” costs). How will the program disposition property and close down the production line? Should also be considered as part of the Life Cycle Cost estimate.
Additional issues to address as it applies to your program—Contract Financing, Progress Payments, Commercial financing, audit impacts (rates and schedules (include number of subcontract audits needed), long lead, termination liability, Buy America, Berry Amendment waiver, warranties and any special terms and conditions for DMS, DCS and shutdown costs.

## Slide 21: Contract Parameters Contract Incentives
  Planned Incentives
  Key program risks & incentives to help mitigate risks & improve probability of success
  Objective Incentives considered & why?
Award Fee
  How is award fees linked to acquisition outcomes—cost, schedule & performance?
  How is award fee tied to specific challenges, commitments & delivered capability versus just “effort”
Are there negative incentives for overrun or poor performance?
If more than one incentive is planned, explain how incentives complement
Why will incentive motivate contractor?
Notes: See AFPAM 63-128, chapter 7, Contractor Incentive Guide for how to approach incentivizing a contractor.

## Slide 22: Intellectual Property (IP) Strategy
  What do you need?
  Technical data rights & deliverables needed throughout system’s life cycle
  What are minimum rights AF can accept
  Summarize prior contracts associated with delivery of technical data & rights in tech data
  How will you buy it?
    Discuss strategy to buy technical data/data rights
    Describe evaluation factors that will be used to assess price & adequacy of technical data during source selection. Discuss use of options for delivery of technical data & obtaining additional rights in technical data.
  Assess merits of including a priced contract option for future (or deferred) delivery of technical data & intellectual property rights.
  Discuss strategy for acquiring SW (source code, documentation, & development artifacts)
How will you manage it?
  What approach will be used to ensure delivery & adequacy of data?
  How will program office verify contractor’s assertion of restricted use & release of data?
See Notes Page
Notes: The Product Data website can provide information:
https://www.my.af.mil/gcss-af/USAF/ep/globalTab.do?channelPageId=s2D8EB9D629AAD6C8012A3858765B1825
Recommend use of Mil-DTL-31000D with ASME Y14.100 (replaces Mil Std 100) and Data Item Description (DID) DI-SESS-8100C/T)
Information on Engineering Data Pricing: The contractor will have to prepare certain data as a natural consequence of contract performance. Design, development, testing, and production tasks will generate certain data, whether or not a requirement is identified in a DD Form 1423 and delivery is requested. This factor is the basis for what is called the "over and above concept" for pricing data; the price paid for a data item will be based on what it costs the contractor to furnish that item, over and above the costs the contractor would incur if it were not required at all.
Rights. The PM shall assess long term data/data rights requirements and corresponding acquisition strategies prior to initiating an RFP to acquire systems or subsystems to ensure they provide for rights, access, or delivery of data that the Government requires for systems sustainment and to maintain competition throughout the life cycle. The PM shall address the data rights strategy including the rationale for acquisition and\or non-acquisition of data and data rights at ASPs and shall document the planning in the Acquisition Strategy and associated data planning documents. Source selections shall consider Government rights to data and include pricing options that correspond to the data and data rights recommended as part of the data strategy. PMs shall also ensure that computer software is acquired as executable code and source code unless documented and approved by MDA. When the contractor is unwilling to provide source code as a deliverable, the PM shall consider software escrow arrangements using mutually agreed to third-party escrow agents.

## Slide 23
Small Business
  What does your Industrial Base Survey indicate is small business (SB) Capability?
Is acquisition appropriate for a SB set-aside?
  If so, what are your recommendations? Breakout opportunities?
Are there any bundling or consolidation decisions?
If no prime opportunities, describe your plan for SB participation
  Identify planned contract incentives to encourage aggressive SB subcontracting
  Identify percentage requirements for SB subcontracting
Discuss your plan for post award monitoring
Notes: As part of the market research, programs should consider small business first
- Ensure NAICS code (dollar value and size standards) and PSC are recommended that broadens competition
If appropriate for SB, provide recommendations
- Review program for any break out opportunities for SB
If not appropriate for SB, describe your subcontracting plan (i.e. contract incentives)
Identify subcontracting requirements…not goals!
How will small business be evaluated in source selection? Factor/sub factor
- FAR Part 15.304 (c)(4), 15.305 (a)(5)
- DFARS 215.04 (c)(i), 215.305 (a)(2)
- PGI 215.304 (c)(i)(A)(5)
Describe your post award monitoring (i.e. CDRL for data)

## Slide 24: Systems Engineering (SE)
Outline open systems architecture approach, combined with technical data rights, Government will pursue in order to ensure a lifetime consideration of competition
  Is there a reference implementation architecture & set of default standards for your domain of operation?
  Modular system & design disclosure: Have you identified key interfaces, data elements & sub-systems that should be open/common/standard?
SE Tradeoff analysis
  Show your approach to determining how cost varies as the major design parameters and time to complete are traded off against each other
Discuss key requirements impacting Acquisition Strategy
  Discuss requirements maturity & stability
  Discuss how Reliability, Availability, & Maintainability are addressed in SRD
Notes: OSD has a requirement at pre MS B for a Systems Engineering Tradeoff Analysis showing how cost and capability vary as a function of the major design parameters; which should be timed to support CDD validation.
For Open Systems Architecture (OSA) guidance/overview, see http://www.acq.osd.mil/se/initiatives/init_osa.html,
and http://openpdq.com/MOSA
Key Interface / Component Designation, consider: Diminishing Manufacturing Sources (DMS), desire to reduce barriers to 3rd party innovation, interfaces driving program cost / performance / supportability, components that change frequently, requirements to be interoperable/net-centric.
Reference architecture and default standards: consult your EN/XR organization to discuss whether there is a default implementation architecture and corresponding set of default open standards to guide your acquisition. If applicable, consider how this guidance could be used in your solicitation to drive openness in key components and interfaces.
Associate contractor agreements that facilitate sharing of data/information should be addressed

## Slide 25: Systems Engineering (cont.)
Discuss status of initial manufacturing concepts & implementation
  What is the status of LRIP manufacturing capabilities & ability to ramp up to full rate production?
  Status of Production Readiness Review
  What are critical manufacturing elements?
  Plans for addressing manufacturability & maturity
Describe key SE components of RFP & contract
  Identify SE RFP requirements & selection criteria
  Identify SE contractual provisions to ensure contractor implements proposed approach
Is configuration management plan required &, if so has one been developed?
  Have defense exportability features been considered in initial designs?
Notes: In discussion of the Acquisition Strategy take the latitude to describe key requirements (KPPs, KSAs), their overall risk to the acquisition, and how they impact cost, schedule and performance. Looking to get an understanding on how the acquisition strategy has been developed to ensure successful execution.
TMRR phase: Discuss status of initial manufacturing concepts. Manufacturing maturity is an important factor prior to MS A and throughout for affordability-capability tradeoffs. For TMRR phase discuss plan for evaluating manufacturing processes and risks.
  Pre-Milestone C (and in some cases MS B): What are key activities required to achieve IOC and FOC? Provide status on key technical reviews conducted: SRR, PDR/CDR, TRR, SVR, PCA/FCA, PRR, etc. How has technical management planning activities changed (organizational and processes)? “Describe interfaces with Prime contractor/vendors. Consider establishing a MOA (Memorandum of Agreement) with DCMA to identify metrics to track contractor progress.
Pre-FRP: What is the status of LRIP manufacturing capabilities and ability to ramp up to full rate production? What are key activities required to achieve IOC and FOC? Provide status on technical reviews conducted (PCA/FCA). How has technical management planning activities changed (organizational and processes)? Has a Manufacturing Readiness Assessment been performed?

## Slide 26: Cybersecurity & Resiliency Acquisition Strategy Panel Chart
CyberSecurity and Resiliency | Authority and Date concurrence | SRD/ Spec | Statement of Objectives (SOO) / Statement of Work (SOW) / Performance Work Statement (PWS) | Request for Proposal (RFP) Section L / Section M | FAR / DFARS / AFFARS Clauses | Sufficiency Assessment
Program Protection |  |  | Ex: Section 2.3 |  |  | Ex: G
Cybersecurity (to include Trusted Systems and Networks (TSN)) |  |  |  |  |  | 
Critical Program Information /Anti-Tamper (AT) |  |  |  |  |  | 
Security Management |  |  |  |  |  | 
Cyber Resiliency |  |  |  |  |  | 
Notes: The ASP consists of a standing panel of senior advisors that are responsible for reviewing the proposed acquisition strategy in order to ensure that all significant considerations associated with a system acquisition have been addressed, including Cybersecurity and Resiliency. The ASP should take place as early as possible in the acquisition planning, and the ASP briefing itself should include a description of how Cybersecurity and resiliency considerations are incorporated into the acquisition strategy. The following is the recommended Cybersecurity and Resiliency chart to include in the technical portion of the ASP briefing.
Has the program completed a Criticality Analysis to inform the system level requirements and system design architecture, based on risk?
Has the appropriate authority agreed per the different tenets below? Who and When?
Per DoDI 5000.01, program managers will employ SSE practices and prepare a Program Protection Plan (PPP) to guide their efforts and the actions of others to manage the program risks to Mission Critical Functions (MCFs), Safety Critical Functions (SCFs), and functions associated with Critical Program Information (CPI). The system security engineer shall populate the ASP chart, and the PM, Director of Engineering (DOE), and Chief Engineer (CE) approve the content of the chart. Once the content of the chart is approved, the slide is presented as a part of the Acquisition Strategy Panel, at which time the PO provides the “sufficiency assessment.”
The content below provides high level guidance for filling out the chart.
The first column (“Authority and Date Concurrence”) is included to ensure that the applicable authorities are in agreement with the strategy for addressing given technical areas. The column should be populated with the name of the authority and the date that they concurred with the approach (e.g., for Critical Program Information/AT, the ATEA’s name and date would be annotated).
The program needs to annotate, in the notes section of the power point, the documentation/artifact(s) with the signatures of the agreement for the Criticality Analysis by the different authorities.
NOTE: Criticality Analysis should be based on MCFs, SCFs, and functions associated with CPI.
The program will fill out the table appropriately with a reference to the location of the section in the Request for Proposal (RFP). If the RFP does not require Cybersecurity and Resiliency requirements, then place “n/a” in the ASP Chart. For more information regarding the appropriate content for the items identified in the first row of the table, please reference the following sections of this document:
2.1 Performance Work Statement (PWS)
2.2 System Requirements Document (SRD) and System Specifications
2.3 Statement of Objectives (SOO) and Statement of Work (SOW)
3.1 Request for Proposal (RFP) – Contract Clauses (NOTE: sections 3.1.1, 3.1.2, and 3.1.3 contain the specifics on recommended lists of FAR, DFARS, and AFFARS Clauses.)
3.2 Request for Proposal (RFP) – Section L
3.3 Request for Proposal (RFP) – Section M
Due to the RFP’s level of maturity, some sections of the table cannot be filled out. In this case, place “applicable” or “not applicable (n/a)” in the chart, and ensure the authorities agree with the applicability determination. As the program matures, populate the table with the highest level of fidelity.
The PO provides a sufficiency assessment based the information provided in the ASP chart. Some examples are listed below:
Green – The RFP package contains adequate cyber language in the RFP agreed by the proper authority per the SSE AG.
Yellow – The Authority has not approved the RFP/Solicitation, but the program has sufficient rationale to proceed. (Recommend rationale be put in notes section of slide)
Red – No cyber language is in the RFP per SSE AG (Recommend rationale be put in notes section of slide)
Additional applicable SSE policy and guidance: DoDI 5000.02, DoDI 5200.39, DoDI 5200.44, DoDI 5200.47E, DoDI 8500.01, DoDI 8510.01, and AFI 17-101.

## Slide 27: Test & Evaluation
T&E Strategy & how it supports acquisition & requirements strategies
Identify issues regarding availability of production representative test articles, test facilities, Systems Integration Labs, Collaborative Development Environments
  Describe capability shortfalls of test ranges
TEMP or Test Plan status?
  Do you have time, budget, & assets required for test
  Are Critical Operational Issues (COIs) linked to Critical Technical Parameters (CTP) & Measures of Effectiveness (MOE)?
Is DOT&E involved? If so, what is position regarding integrated testing economies
  What specific challenges are addressed through your test strategy?
  How have you incorporated M&S into your strategy & what challenge does this address?
Notes: T&E is more than just DT and OT (we have contractor testing, IA testing, interoperability, etc, all of which must be integrated). The TEMP, acquisition strategy, and requirements need to be in sync with each other. A TEMP must be prepared for a MS A decision.
Discuss your approach (pros/cons) for reducing test time and redundancies. Specifically explain how this is going to reduce testing cost and schedule as applicable and emphasize what specific buy-in you have from key stakeholders: AFOTEC, DOT&E, and/or AF/TE.
Has an Integrated Test Team (ITT) been formed and a charter signed?
Has the TEMP been fully coordinated? What are the open issues, if any? When will it be completed?
Have you assessed the Critical Operational Issues, Critical Technical Parameters, and Measures of Effectiveness? Are they linked and achievable based on the schedule/funding estimates? Are there any high-risk areas that lower the probability of success?
Identify the Responsible Test Organization (RTO) and the operational test organization (i.e., AFOTEC or MAJCOM) according to AFI 99-103.
In describing capability shortfalls of the test ranges keep in mind that some new technologies require test resources that do not yet exist or do not exist in a form appropriate for final DT/OT (e.g. directed energy). Have you had input from the test community (or an experienced tester?)
How will M&S be used in your tests? Does it replace or supplement. Also what challenge does it create? Are the M&S tools validated? How will the data to support the models be generated?
PM’s are required by AFI 99-103 to attempt to use government test facilities as the first choice. If these facilities are not used PM should inform the ASP panel on rationale.

## Slide 28: Guardrails
Thresholds that trigger notification to MDA regarding cost, schedule, &/or performance breaches
Guardrails as measured against majority of contractors exceeding following thresholds:
  Cost: (be specific with cost number & percentage)
  Schedule: (be specific with date & timeline)
  Performance:
PM will notify MDA if…
Guardrails provide an additional layer of checks and balances
Notes: T&E is more than just DT and OT (we have contractor testing, IA testing, interoperability, etc, all of which must be integrated). The TEMP, acquisition strategy, and requirements need to be in sync with each other. A TEMP must be prepared for a MS A decision.
Discuss your approach (pros/cons) for reducing test time and redundancies. Specifically explain how this is going to reduce testing cost and schedule as applicable and emphasize what specific buy-in you have from key stakeholders: AFOTEC, DOT&E, and/or AF/TE.
Has an Integrated Test Team (ITT) been formed and a charter signed?
Has the TEMP been fully coordinated? What are the open issues, if any? When will it be completed?
Have you assessed the Critical Operational Issues, Critical Technical Parameters, and Measures of Effectiveness? Are they linked and achievable based on the schedule/funding estimates? Are there any high-risk areas that lower the probability of success?
Identify the Responsible Test Organization (RTO) and the operational test organization (i.e., AFOTEC or MAJCOM) according to AFI 99-103.
In describing capability shortfalls of the test ranges keep in mind that some new technologies require test resources that do not yet exist or do not exist in a form appropriate for final DT/OT (e.g. directed energy). Have you had input from the test community (or an experienced tester?)
How will M&S be used in your tests? Does it replace or supplement. Also what challenge does it create? Are the M&S tools validated? How will the data to support the models be generated?
PM’s are required by AFI 99-103 to attempt to use government test facilities as the first choice. If these facilities are not used PM should inform the ASP panel on rationale.
Consider to Spectrum Supportability Risk Assessment and Equipment Spectrum Certification Stage status as part of the thresholds. SSRA are part of the items used during milestone decisions. ESC has an impact on performance breaches and schedule is not address early on time.

## Slide 29
Documentation Plan
Required Acquisition Documentation | S/R 804 | Tailoring |  | Requested Tailoring for Rapid Prototyping | 
 |  | Approval | Milestone Required | Approval | Date Required
2366a/b certification | - | MDA | MS A | Not Required for non-MDAP Program | 
Acquisition Decision Memo | R | MDA | MS A | MDA | Prior to PL Solicitation Release
Acquisition Strategy Document | S | MDA | MS A | MDA | Prior to PL Solicitation Release
Affordability Analysis | R | MDA | MS A | Defer to Development/Production | 
Bandwidth Requirements Review (part of ISP) | R | Not Addressed in MDD |  | AF CIO | Prior to PL OT Award
Capability Development Document | R | AFROC | MS A | Defer to Development/Production | 
Clinger-Cohen Act Compliance | S | MDA; AF CIO | MS A | MDA; AF CIO | Prior to PL OT Award
Concept of Operations | R | USSTRATCOM | MS A | USSTRATCOM | Approved Feb 2018
Core Logistics Determination (Part of LCSP) | S | MDA | MS A | PEO | Prior to PL OT Award
Cost Analysis Requirements Description | R | PEO | MS A | PEO | Prior to PL Solicitation Release
Cybersecurity Strategy (Part of PPP) | R | AF CIO | MS A | AF CIO | Prior to PL OT Award
DoD Component Cost Estimate | R | AFCAA | MS A | AFCAA | Prior to PL Solicitation Release
DOT&E Report on Initial Operational Test and Evaluation | S | Not Addressed in MDD |  | Defer to Development/Production | 
Frequency Allocation Application (DD Form 1494) | S | NTIA | MS A | NTIA | Prior to PL Delivery
Full Funding Certification Memo | - | MDA; AF CFO | MS A | Not Required for non-MDAP Program | 
Independent Cost Estimate | - | DCAPE | MS A | Not Required for non-MDAP Program | 
Independent Logistics Assessment | - | Not Addressed in MDD |  | Not Required for non-MDAP Program | 
Independent Technical Risk Assessment | - | DAE | Dev RFP Release | SAF/AQR | Prior to ASP
Information Support Plan (Includes BRR) | R | Not Addressed in MDD |  | AF CIO | Prior to PL OT Award
Tailor documents based on program need
Be prepared to discuss justification for tailoring strategy
EXAMPLE - For discussion purposes only
Consider SSRA and ESC status.

## Slide 30
Documentation Plan (cont.)
Required Acquisition Documentation | S/R 804 | Tailoring |  | Requested Tailoring for Rapid Prototyping | 
 |  | Approval | Milestone Required | Approval | Date Required
Information Technology and National Security Systems Interoperability Certification | R | Not Addressed in MDD |  | Defer to Development/Production | 
Item Unique Identification Implementation Plan | R | Deferred to MS B |  | Defer to Development/Production | 
Life Cycle Mission Data | R | Deferred to MS B |  | Defer to Development/Production | 
Life-Cycle Sustainment Plan (Includes Core Determination) | R | Deferred to MS B |  | Defer to Development/Production | 
Operational Test Agency Report of OT&E Results | R | Not Addressed in MDD |  | Defer to Development/Production | 
Operational Test Plan | S | Not Addressed in MDD |  | Defer to Development/Production | 
PESHE and NEPA/E.O. 12114 Compliance Schedule | S | Not Addressed in MDD |  | CAE | Prior to PL Delivery
Preservation and Storage of Unique Tooling Plan | - | Not Addressed in MDD |  | Not Required for non-MDAP Program | 
Program Protection Plan (Includes Cybersecurity Annex) | R | Deferred to MS B |  | AF CIO | Prior to PL OT Award
Prototype Plan | - | Not Addressed in MDD |  | PM | Prior to PL Solicitation Release
Prototype Requirements Document | - | Not Addressed in MDD |  | PM | Prior to PL Solicitation Release
Request for PL Prototype Proposal | R | MDA | MS A | PEO | Prior to PL Solicitation Release
Should Cost Target | - | Deferred to MS B |  | Not Required for non-MDAP Program | 
Spectrum Supportability Risk Assessment | R | AF CIO | MS A | AF CIO | Prior to PL Delivery
Systems Engineering Plan | R | Deferred to Dev RFP Release |  | Defer to Development/Production | 
Technology Readiness Assessment | R | Not Addressed in MDD |  | Defer to Development/Production | 
Technology Targeting Risk Assessment (Part of PPP) | R | DoD Component | MS A | DoD Component | Prior to PL OT Award
Test and Evaluation Master Plan | R | Deferred to Dev RFP Release |  | Defer to Development/Production | 
Validated Online Lifecycle Threat Report | R | NASIC | MS A | NASIC | Prior to PL Solicitation Release
Tailor documents based on program need
Be prepared to discuss justification for tailoring strategy
EXAMPLE - For discussion purposes only

## Slide 31: “What Worries Me”
Opportunity to communicate internal concerns to SAE
Discuss any issues that are concerning to PEO & PM:
  Funding Instability
  Technical Transition Issues
  Congressional Interest
  Requirements Stability
Notes: "What worries me"? The PM/PEO are encouraged to identify issues that provide the most concern. It is an open opportunity to identify: "what worries me most”. What "keeps me up at night"? These may include oversight issues, funding instability, congressional interest, or other issues such as slow transition of technology. This is an opportunity for the PM/PEO to notify the SAE of potential issues either not addressed previously, or reiterate some of those addressed earlier. Identifying these issues is the first step; but have a plan to address them. Also, identify how the SAE might help. An example might be asking the SAE to break a logjam disagreement with the OSD staff. Another might be a problem getting coordination through another Air Force Directorate (GC, TE, IL etc).
Consider where the PO is on the Spectrum Supportability Risk Assessment. Consider how Equipment Spectrum Certification Stages can have an impact on schedule and cost if not address on time.

## Slide 32: Recommendation & Way Forward
Recommendation
Designate Program an MTA/Section 804
Approve Acquisition Strategy
Delegate Rapid Prototyping solicitation release and selection authority
Way Forward
Discuss noteworthy milestones &/or required engagements with MDA

## Slide 33: Back-Up
See Footnotes for additional information
Notes: International Cooperation, Systems Assessment, manpower/experience and the other topics included in Back-up should be moved forward to the basic briefing when they are a “key part” that needs to be addressed in the Briefing. BUT keep in mind the 1 ½ hour limit to the briefing.

## Slide 34: Middle Tier of Acquisition (MTA) – Program Identification (1)
Middle Tier of Acquisition (MTA) – Program Identification |  | 
By submitting this Program Identification form, the DoD component is identifying a new MTA program to the Office of the Secretary of Defense (OSD). This data will ultimately be collected via the Defense Acquisition Visibility Environment (DAVE). |  | 
Submitted By: |  | 
Effective Date (mm/dd/yyyy): |  | 
Program Information: |  | 
Program Type: | Select | 
Program Long Name: |  | 
Program Short Name: |  | 
Program Description: |  | 
Lead Component: | Select | 
Program Executive Office: | Select | 
MTA Program Management Office: |  | 
POC Name and Rank: |  | 
POC Phone: |  | 
POC Email: |  | 
Antecedent System: |  | 
Capability Requirement: | Please note: Fill out the first column with the primary Joint Capability Area. If the program has additional secondary Joint Capability Areas, additional columns are available to the right. | 
Joint Capability Area(s): | Select | Select
Requirements Document: | Select | 
If "Other", indicate document type: |  | 
Validation Authority: |  | 
Date Approved (mm/dd/yyyy): |  | 
Program Quantity: |  | 
Expected Rapid Prototype Quantity: |  | For an MTA program, these quantity types should be considered mutually exclusive.
Expected Rapid Fielding Quantity: |  | 
Additional Guidance/Information located at Secretariat SharePoint:
https://cs2.eis.af.mil/sites/10263/dir/integration/execution/Secretariat/Forms/AllItems.aspx

## Slide 35: Middle Tier of Acquisition (MTA) – Program Identification (2)
Program Schedule: |  | 
MTA Designation Date (mm/dd/yyyy): |  | Once MTA Designation Memorandum is signed, Components must attach a copy of the decision document with this form.
Date Funds First Obligated (mm/dd/yyyy): |  | Date funds first obligated will act as the “program initiation” and will start the five-year clock for the Middle Tier of Acquisition programs, as prescribed in statute.
Expected Initial Production Date (mm/dd/yyyy): |  | DoD requires that rapid fielding programs enter into initial production within six months of date funds first obligated.
Expected Date of Operational Demonstration (mm/dd/yyyy): |  | The objective of an acquisition program under a rapid prototyping pathway shall be to field a prototype that can be demonstrated in an operational environment and provide for a residual operational capability within five years of the date funds first obligated
Expected Program Completion Date (mm/dd/yyyy): |  | The program must complete prototyping/fielding within 5 years to be an MTA program. If the PM expects the program to exceed this 5 year cap, it can no longer be an MTA program.
Technology: | Please note: Fill out the first column with the primary Technology Area. If the program has additional secondary Technology Areas, additional columns are available to the right. | 
Technology Component and/or System: | Select | Select
Current Technology Readiness Level(s) (TRL): | Select | Select
Expected Technology Readiness Level(s) (TRL): | Select | Select
Description of Technology, Component, or System: |  | R&E recommended as text field ~1000 character limit
System Complexity / Design / Demo Scope: |  | From R&E: This section should address the level of integration needed to make the system effective and what kind of demo may be needed to prove it. We want warfighter capability at program completion (and knowledge along the way). ~1500 character limit
Manufacturing Readiness Level (MRL): | Select | 
Additional Guidance/Information located at Secretariat SharePoint:
https://cs2.eis.af.mil/sites/10263/dir/integration/execution/Secretariat/Forms/AllItems.aspx

## Slide 36: Middle Tier of Acquisition (MTA) – Program Identification (3)
Performing Activity: |  | 
Has the performing activity been identified? | Select | Performing activity could include government performing activity, academia, or a contractor.
If yes, performing activity CAGE Code: |  | http://www.govcagecodes.com/
Contract(s): | Please note: Fill out the first column with the primary contract. If the program has additional secondary contracts, additional columns are available to the right. | 
Contract Strategy: | Select | Select
Contract Type: | Select | Select
Contract Lifecycle Phase: | Select | Select
Contract Number: |  | 
Contracting Office: |  | 
Outcome: | Please note: Outcome section is only required upon program completion | 
Outcome: | Select | Once MTA Outcome Decision is signed, Components are required to upload the document to the Acquisition Information Repository (AIR).
If transitioned, identify program: |  | 
Date of MTA Outcome Decision Memorandum (mm/dd/yyyy): |  | 
Reason for Outcome: | Select | 
If "Other" reason for outcome, specify: |  | 
Sustainment: |  | 
Field Sustainment Responsibility: | Select | 
Depot Sustainment Responsibility: | Select | 
Supply Chain Responsibililty: | Select | 
Expected Service Life (Years): | Select | 
Technology Data Rights: |  | 
Additional Guidance/Information located at Secretariat SharePoint:
https://cs2.eis.af.mil/sites/10263/dir/integration/execution/Secretariat/Forms/AllItems.aspx

## Slide 37: Middle Tier of Acquisition (MTA) – Program Identification (4)
Program Budget: | Please note: Fill out the first column with the primary funding account. If the program has additional funding lines, additional columns are available to the right. |  |  |  |  |  |  |  | 
Appropriation Category(s): | Select | Select | Select | Select | Select | Select | Select | Select | Select
Account Code(s): | Select | Select | Select | Select | Select | Select | Select | Select | Select
Account Name(s): | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Budget Activity(s): | Select | Select | Select | Select | Select | Select | Select | Select | Select
Program Element/Line Item(s): |  |  |  |  |  |  |  |  | 
Project Code(s): |  |  |  |  |  |  |  |  | 
Program Budget Details: |  |  |  |  |  |  |  |  | 
Budget Year: | Select | Budget Estimate includes prior year actuals and current budget authority, FYDP budget, and PM's estimate to complete beyond the FYDP. |  |  |  |  |  |  | 
Budget Position: | Select |  |  |  |  |  |  |  | 
TY $M | Prior | FY2019 | FY2020 | FY2021 | FY2022 | FY2023 | FY2024 | To-Complete | Total Budget
RDT&E: |  |  |  |  |  |  |  |  | $ -
Procurement: |  |  |  |  |  |  |  |  | $ -
Acquisition O&M: |  |  |  |  |  |  |  |  | $ -
MILCON: |  |  |  |  |  |  |  |  | $ -
Sustainment O&M: |  |  |  |  |  |  |  |  | $ -
MILPERS: |  |  |  |  |  |  |  |  | $ -
Total: | $ - | $ - | $ - | $ - | $ - | $ - | $ - | $ - | $ -
Additional Guidance/Information located at Secretariat SharePoint:
https://cs2.eis.af.mil/sites/10263/dir/integration/execution/Secretariat/Forms/AllItems.aspx

## Slide 38: Back-ups
Program Office
Industrial Base Capability & International Cooperation
Risk
Additional Acquisition Topics
Samples
  Affordability
  Should Cost
  Source Selection
  Acquisition Strategy

## Slide 39: Program Office Organization, Experience, & Manpower
  Provide Organizational Structure (Org Chart)
Resources
  Address Critical manpower positions / program office manning & facilities
    Program Office Staffing & Support Contractor Resources Available to PM
      Identify Deputy PM, chief program engineer, lead program system engineer, lead cost analyst, product support manager and engineering data management officer (EDMO), contracting officer, financial manager, T&E
      Identify any shortage of personnel
  Identify current DAWIA (APDP) certification levels for all key government personnel (SPMs, PMs, etc)
Integrated Product Teams (IPTs)
PMA tenure agreement
Notes: Is the lead cost analyst an organic resource? Reference December 22, 2008 AT&L Memorandum on Restructuring of the Acquisition, Technology and Logistics Business, Cost estimating and Financial career field.

## Slide 40: Program Org Chart
SAF/AQ
PEO
Lt Gen JP Jones
PM
Col John Smith
Program
Control
Maj D. MacArthur
Contracts
Ms. Jane Smith
Sys Eng
Maj Kelly Johnson
Test
Maj C. Yeager
Test IPT
2 Captains
1 GS-12
5 Contractors
PC IPT
2 Captains
1 GS-12
5 Contractors
Contracts IPT
2 Captains
1 GS-12
Sys Eng IPT
2 Captains
1 GS-12
5 Contractors
ACC/A5XX
Col B Martin
OO-ALC/XYZ
Col Al Griggs
User
Depot
PSM
Lt. Col T. Jones
Support IPT
1 Captain
1 GS-12
4 Contractors
Notes: Use existing program org charts so long as they show from MDA through PM and major IPTs within the program office.
In no case shall there be more than two levels of review between the Program Manager and the Milestone Decision Authority in accordance with DODD 5000.01, DODI 5000.02, and AFPD 63/20-1.
Include in your chart the Program Control Office, if you have one.

## Slide 41: Industrial Base Capability and International Cooperation
  Industrial Capability
  Address industry’s capability to design, develop, produce, support (product technology obsolescence, replacement of limited-life items, regeneration options for unique manufacturing processes, and conversion to performance specifications at the subsystems, component, and spares levels) , and, if appropriate, restart a program.
  Address the need for government action necessary to ensure a robust US Industrial and Technical base
    Are new industrial base capabilities required? US or off-shore manufacturing?
    Diminishing Manufacturing Sources (DMS)
      Do you have sufficient data and data rights for DMS?
  International Cooperation/Foreign Military Sales
  Defense Exportability considered in the design of the system?
  See Notes section to address these topics
Notes: 10 U.S. C. Sec. 2440. - Technology and Industrial Base Plans
The SecDef shall…require consideration of the national technology & industrial base in the development & implementation of acquisition plans for each MDAP
Address current or potential FMS customers and impact of industrial base
US Code SEC. 2350 a requires that at MS A that cooperative opportunities be considered and a Cooperative Opportunities Document be prepared
  Address the possibility for cooperative research and development opportunities
    Indicate any limitations on foreign contractors being allowed to participate at the prime contractor level.
  Summarize any plans for cooperative development with foreign governments or cognizant organizations.
  Summarize plans to increase the opportunity for coalition interoperability
Foreign Military Sales (FMS)
  Specify potential or plans for FMS and/or Direct Commercial Sale and the impact upon program cost due to program protection and exportability features.
  Current OSD emphasis on the incorporation of defense exportability features in initial designs.

## Slide 42: Additional Acquisition Topics (if not addressed elsewhere)
Program Protection Planning
  Anti-Tamper
  Protection of Critical Program Information
Information Assurance
Trusted Foundry
Clinger Cohen Act Certification progress (CCA)
Environmental & Manufacturing/Quality Engineering
Interdependencies/Interoperability
Information Technology
Human Systems Integration
Environment, Safety, Occupational Health
Spectrum Management/Supportability
Integrated Digital Environment Management (may address in the data rights section)
Government Furnished Equipment/Property
Modeling and Simulation
Corrosion Control
Intelligence Mission Data (IMD)
Notes: What are the Clinger Cohen Act certification issues associated with your program? If the strategy is being developed to release an RFP prior to a milestone, you should still explain the plan for meeting your certification requirements. Teaming early with the AF-CIO precludes surprises and stumbling blocks as your program nears a significant milestone event.
Explain how you have assessed intelligence supportability
  Describe the process used and personnel involved in assessing intelligence supportability
  Summarize the types of intelligence products and services required to support the program across the life-cycle
  Summarize intelligence shortfalls
  Summarize cost, schedule and/or performance risk associated with intelligence shortfalls
  Describe plan to mitigate intelligence shortfalls
Explain how threat data is being used and managed
  Describe threat data sources and application
  Describe plan to manage the threat baseline throughout the acquisition life-cycle
  Describe plan to ensure testing is accomplished against a realistic threat environment (test to threat baseline, developmental scenario=operational test scenario)
If you expect to have ASIC (application specific integrated circuits) then go to :Trusted Foundry: http://www.manufacturingnews.com/news/040203/art1.html

## Slide 43: Technology Readiness
Critical Technology Element | TRL | Incr 1 | Incr 2
 | 9 | X | 
 | 6 |  | X
 | 9 | X | 
 | 8 | X | 
 | 9 | X | 
 | 9 | X | 
 | 7 |  | X
 | 5 |  | X
 | 6 |  | X
 | 6 |  | X
 | 9 | X | 
 | 6 | X | 
 | 9 | X | 
 | 8 | X | 
 | 8 | X | 
Technology Readiness Levels (TRL)
9. Actual system “flight proven” through successful mission operations
8. Actual system completed and “flight qualified” through test and demo
7. System prototype demonstration in a operational environment
6. System/subsystem model or prototype demonstration in a relevant environment
5. Component and/or breadboard validation in relevant environment
4. Component and/or breadboard validation in laboratory environment
3. Analytical and experimental critical function and/or characteristic proof-of-concept
2. Technology concept and/or application formulated
1. Basic principles observed and reported
Sample Chart
See Notes Page
Notes: List key program technologies; current TRLs. TRL 6 is required by MS B. If a technology is below TRL 6 summarize the technology maturation approach (pre-MS A) or summarize the verification of the technology maturation (pre-MS B/C)
List TRL level for critical technologies which may impact meeting a KPP , KSA or APA thresholds or represent risk to deliver capability on schedule and budget
Recommend explaining maturity plans for any CTEs that are not at the requisite level when the review takes place (i.e. TRL 6 at MS B, TRL 7 at MS C).
The category of Technology identifies the key technologies necessary for this program. Column 2 the TRL and the next two columns in this sample (showing two increments) provides the increment in which the technology will be delivered.
This sample generally applies to hardware
Additionally you may want to utilize the Technology Development and Transition Strategy (TDTS) Guidebook, which can be found at the DAU website.
(See OSD AS Template para 6.3)

## Slide 44
Product Support Strategy
Metric | Antecedent Actual | Original Goal | Current Goal | Current Estimate/ Actual
Materiel Availability | 76% | 80% | 77% | 71%
Materiel Reliability | 37 hrs | 50 hrs | 50.5 hrs | 48 hrs
Ownership Cost | 245.6B | 385.5B | 395.1B | 395.1B
Mean Down Time | 12 hrs | 20 hrs | 18 hrs | 15 hrs
Metrics Data
* Test or fielding event data derived from _______
Notes:
Sustainment Schedule
O&S Data
MS B
MS C
IOC
FRP
FOC
Sustainment
BCA
LCSP
CLS Start
Depot Standup
LRIP Contract Award
Blended Partnership Startup
PBL Recompete
Avionics PBL
PBL Recompete
Sustainment Approach
  Current (initial CLS covering total system)
  Future (sub-system based PBL contracts)
Issues
  Shortfall in O&M funding in FYDP
  Reliability and availability estimates are below goals
  LCSP requires update before DAB
Resolution
  POM request for O&M restoration submitted
  Reliability improvement plan with clear RAM goals up for final signature
  LCSP in draft
BCA
BCA
BCA
Cost Element | Antecedent Cost | ABC Original Baseline | ABC Current Cost
1.0 Unit-Level Manpower | 3.952 | 5.144 | 5.750
2.0 Unit Operations | 6.052 | 6.851 | 6.852
3.0 Maintenance | 0.739 | 0.605 | 0.688
4.0 Sustaining Support | 2.298 | 2.401 | 2.401
5.0 Continuing System Improvements | 0.129 | 0.025 | 0.035
6.0 Indirect Support | 1.846 | 1.925 | 1.956
Total | 15.046 | 16.951 | 17.682
Cost based on average annual cost per squadron
Total O&S Costs | Antecedent | ABC
Base Year $M | 102,995.2 | 184,011.9
Then Year $M | 245,665.3 | 395,147.2
Today
Notes: The information requested is from paragraph 7.4 of the OSD Acquisition Strategy Template
Top Left Quad: Product Support Strategy: Purpose: Programs cite current sustainment philosophy and any future differences
Fields: Sustainment Approach
    Current: State what the current planned or actual maintenance support strategy is (e.g..: Initial 4 year CLS period; core)
    Future: State planned strategy for future if different than current strategy
  Issues: Cite any sustainment issues the program is currently experiencing or projected risks (50/50 assessment; DMS Considerations
  Resolution : Identify planned or potential resolutions to noted issues
Bottom Left Quad: Sustainment Schedule: Purpose: Display planned logistics schedule milestones
Fields: Top Bar (Milestones)--Begin from present (or slightly earlier) through expected life of the system. Include major events: e.g., MSs, IOC, FOC, etc. Events--Ensure important life cycle sustainment events are listed in the chart; e.g., BCAs, PBL decisions, CLS periods
Top Right Quad: Metrics Data: Purpose: Display current estimates of sustainment metrics vs. goals and antecedents
Fields: Metrics-- At a minimum, address four metrics shown. See CJCSI 3170.01G; May include other metrics e.g., logistics footprint, customer wait time, etc.
  Antecedent Actual--Evaluation of the four metrics on the preceding (antecedent) system (e.g. F-15 vs. F-22 or SSN 688 vs. SSN 774); Antecedent is the system cited in Selected Acquisition Report (SAR) to Congress
  Original Goal-- Value for each metric according to the original baseline goal submitted for the first sustainment metrics transmittal
  Current Goal--Value for each metric according to the current baseline goal for sustainment
  Current Estimate--Program evaluation of system performance or projected performance (if still in development) for each metric
    Color rating assigned by PM (estimate vs. goal); Green – At or exceeding goal; Yellow – Below goal by < 5%; Red – Below goal by > 5%
  Test or Fielding Event Data Derived From
    Cite the event (OPEVAL, IOT&E, etc.) or modeling and simulation tool that led to the current estimate
  Notes: Any relevant or pertinent information concerning metrics definitions
Bottom Right Quad: O&S Data:
Fields: Fields are primarily pulled from the SAR O&S section:
  Cost Element--Refer to 2007 CAIG (now CAPE) Cost Estimating Guide for definitions of individual cost elements
    These definitions should be consistent with what is submitted in the program’s SAR O&S cost section (which should be based on identical definitions)
  Antecedent Cost--O&S cost of the existing program reported using the CAPE cost elements
    O&S costs are based on average annual cost per hull, squadron, brigade, etc.
      Use the SAR as the basis for determining the unit level and cite beneath first box what costs are based on
  New Program Original Baseline--New program O&S cost broken out over the CAPE cost elements, according to their original SAR submission.
    Costs are based on average annual cost per hull, squadron, brigade, etc.
  New Program Current Cost--Current program cost broken out over CAPE cost elements per the most recent projections – not last SAR submission
    Costs are based on average annual cost per hull, squadron, brigade, etc.
    Color rating assigned by PM, based on increase since original baseline: Green – At or below original baseline or < 10% increase
      Yellow – Increase > 10% but < 20% vs. original baseline : Red – Increase > 20%
  Total O&S Costs--Comparison of antecedent program cost vs. the new program’s current cost presented in totals in both TY$ and BY$
    For the new program, use the most recent estimate, not the most recent SAR values
    O&S cost totals should be consistent with the CAPE estimate
    Depot activation funding

## Slide 45
Risk ID & Title / Category |  | 
Risk Statement: E.g.., Cost proposal exceeds budget |  | 
Impact: Address impact of risk |  | 
Likelihood: 4 | Consequence: 4 | Risk Rating: High (Red)
Risk Management: Address mitigation approach (Describe risk handling plan, milestones and risk closure criteria. Specifically address cost, schedule and performance impacts and cost/schedule reserve (margin). Indicate what resources are required to cover the risk. What is the the performance impact?) |  | 
Post Risk Management Rating: Likelihood=1, Consequence =2 (GREEN) |  | 
All High & Moderate Risks should be identified. Recommend Program Office prepare a Risk Mitigation chart & provide in back-up
Risk Mitigation
Notes: This slide shall be generated for each moderate or high risk identified in the preceding Risk Summary slide. (for Briefing purposes only those risks briefed (Red and top yellows) would be included in the main body of the Briefing—all others will have a “Risk Management Mitigation” slide included as back-ups. )
Risk ID, Title and Category are the same as on the preceding chart(s)
Risk Statement: An adverse event that impacts the ability to obtain the requirement. Worded as an event that might occur in the future.
Impact Statement: Worded in programmatic and/or operational terms.
Likelihood: Range of probability (reference standardized matrix and definitions)
Consequence: Range of severity (reference standardized matrix and definitions)
Initial Risk Rating: (High, moderate, or low) corresponding to colors red, yellow, and green
Risk Management (Handling Plan): Describes what you’re going to do to try to avoid having the risk event occur (lower the probability) and/or reduce impact if the risk event occurs.
Post Risk Management Rating: The risk rating assigned after planned mitigation efforts (the anticipated risk assessment if the Risk Management Plan and Mitigation plans are effective as thought).

## Slide 46: Should Cost Summary
Planned
FY16-FY18: $70.292M; EMD Phase 2 (Contract Award) Source Selection Savings
FY 17: $24.500M; Flight Body-2
FY18: $26.000M; EMD Phase 2 Test Activities
Realized
FY13: $ 1.400M; EMD Phase 1 Aircraft Integration
FY13: $11.000M; EMD Phase 1 Test Activities
See Notes Page
Ensure all Should Cost Initiatives are PEO-Approved in CCaRS and values are consistent. Use Back-up slides to elaborate on each initiative.
Notes: This chart is an example of how a summary of should-cost initiatives could look from a funding impact perspective.
Should-Cost initiatives must be PEO-approved and must match the values in CCaRs. If not PEO-approved in CCaRs, the should-cost initiative cannot be presented in the ASP. This is to keep reporting consistent across HAF. Should-Cost initiatives should be clearly identified as either realized or planned.
Be prepared to explain how you’ve coordinated should-cost initiatives with stakeholders (i.e. TE, O&S, Depot)
Be clear if the cost savings are against the total weapon system or just the increment in question for this briefing (i.e. O&S for modernization programs).
Use example in backup to elaborate on individual should cost initiatives if desired.
See latest guidance from SAF/AQ at AECO website:
SAF/AQ memo: Updated Should Cost Management Guidance and Business Rules, date November 6, 2014 and SAF/AQ
Should Cost Management (SCM) Guidance and Business Rules, dated October 2014
As an alternative, charts that are presented at a Milestone DAB (see ASP charts in backup) can be used.
Examples of Supporting Evidence for Should Cost: Shorten program timeline; Historical cost, learning curve, and understanding of production efficiencies; Long-term supplier agreements; Open system architecture design eases future enhancements; Aggressive “Breakout” IPT established for appropriate technical data packages (TDP) and data rights