Record of Changes.

| Record of Changes |
| --- |
| Version | Effective Date | Summary |
| 1.0 | 26 Aug 2013 | Basic Document; Approved by S&P Board on 18 Jul 2013. |
| 1.1 | 17 Jun 2013 | Minor update in metric reporting procedures; Development Planning WBS reference correction; updated reference links; and adds ESOH to the team structure |
| 1.2 | 16 Jun 15 | Updated reference links in sections 7.0 (Tools) and 8.0 (Training) |

Pre-Milestone A Product Support

- Description

  - Identified in this standard process are the Development Planning (DP) subset Product Support (PS) activities required to support a Materiel Development Decision (MDD), and after MDD the PS activities required to support the Milestone A event.  DP is the first opportunity in the weapon system life cycle to influence PS for programs.  Decisions made during this acquisition phase ultimately drive PS cost and performance considerations for the entire life of the program.

  - Documented Documented in this standard process version are the PS specific activities for AFLCMC when a customer operational MAJCOM (e.g., ACC, AMC, AFGSC, AETC) formally requests a DP effort where there is no established acquisition program.  The AFLCMC entity responsible for the overall AFLCMC DP effort leading up to MDD is XZ, specifically XZA for Aerospace Systems development, XZC for Electronic Systems Development, and XZW for Armament Systems development.  XZA, XZC, and XZW are the organizations where the Program Manager resides, and have overall responsibility in working with the appropriate functionals for DP-related PS planning.  After MDD, the responsibility transfers to the respective AFLCMC weapon system Program Executive Officer (PEO) as the weapon system specific Program Office is stood-up.

  - Future versions of this standard process will address Pre-Milestone A PS for established acquisition programs and Defense Business Systems (DBS).

- Purpose

  - During the FY12 preparation for the Air Force Life Cycle Management Center stand-up, HQ AFMC formed a Life Cycle Management Working Group (LCM WG) to investigate specific PS processes, which included DP. A DP-sub team was formed with the objective of evaluating and recommending improvement to DP governance, processes, and roles/responsibilities by incorporating PS considerations. The DP sub-team concluded PS is inconsistently and thinly considered during DP.

  - The DP sub-team key recommendations were presented to AFMC/CC on 13 Sep 2012, and were approved.  The key DP sub-team recommendations are:

    - AFLCMC inject PS considerations at relevant internal & external review

    - AFLCMC leverage external PS expertise, to include AFSC, into DP efforts

  - In order to implement the LCM WG DP key recommendations, this PS process identifies the augmentation of the DP effort with a Development Planning Product Support Team (DPPST), which will implement the LCM WG DP key recommendations.  The DPPST will first form to accommodate Materiel Development Decision (MDD) requirements.  After MDD, the DPPST will adjust its membership to accommodate Milestone A requirements.  A detailed description of the functional DPPST is provided in Section 4.4 and all Roles and Responsibilities are identified in Section 6.0

- Potential Entry/Exit Criteria and Inputs/Outputs.

  - Entry Criteria:

    - Customer operational MAJCOM request for Development Planning effort

    - After MDD,  Customer operational MAJCOM funding/desire to proceed to Milestone A

  - Exit Criteria:

    - MDD Acquisition Decision Memorandum (ADM) signed by the Milestone Decision Authority

    - After MDD, Milestone A ADM signed by the Milestone Decision Authority

  - Inputs: Capabilities Based Assessment (CBA); Initial Capabilities Document (ICD); PS requirements; key parameters/attributes; Measures Of Suitability (MOS); analogous systems performance data and documented sustainment issues

  - Outputs: Initial PS strategy; Depot Source of Repair (DSOR) planning core applicability; technical data rights strategy; Life Cycle Sustainment Plan (LCSP); Item Unique Identification (IUID) Implementation Plan;  PS assessment of required Milestone A documents

- Process Workflow and Activities.

  - Supplier, Inputs, Process, Outputs, Customer (SIPOC), Table 1.

  - Process Flowcharts.  The process flowchart, Figure 1, represents the high level DP process flow from customer operational MAJCOM DP request to MDD.  Figure 2 depicts the high level PS process flow from customer operational MAJCOM DP request to Milestone A.  As a subset of the DP process, Figure 3 details the PS specific 1.0 WBS events that lead up to MDD.   MDD to Milestone A PS WBS events are further defined at Figure 4.

  - Work Breakdown Structure (WBS).  The WBS, Table 2, provides additional detail on the activity boxes in the flowcharts. The MS Excel version of the WBS, Attachment 1, provides more detail.

Table 1. SIPOC

| Supplier | Inputs | Process | Outputs | Customer |
| --- | --- | --- | --- | --- |
| Customer MAJCOM | Weapon system mission shortfall/gap | Identify system requirements; identify PS requirements; JCIDS Process | Capabilities Based Assessment (CBA); Initial Capabilities Document (ICD) RE: WBS 1.4 | Program Development Directorate/ Program Office |
| Customer MAJCOM; DoD/USAF policies | Customer PS requirements | Identify PS strategy based upon PS requirements and CBA/ICD | PS Strategy RE: WBS 1.6.9 | Concept Developers; Program Manager; Customer MAJCOM; PSM |
| Legal Advisor; Contracting Officer; Sustainment Engineering; PM; PSM | PS Strategy; LCSP (draft) | DoDI 5000.02; DoDI Technology Development Strategy Template; FAR; DFAR; AFFAR; Legal advice | Technical Data Rights Strategy RE: WBS 2.6 | Program Manager; PSM; Sustainment Engineering |
| Program Manager; PSM; Customer MAJCOM | Weapon system concept information; Vision/strategy on how to manage the 12 PS elements | DoD Life Cycle Sustainment Plan (LCSP) template; AFI 63-101/20-101; AFPAM 63-128 | Life Cycle Sustainment Plan (LCSP) RE: WBS 2.7 | Program Manager; PSM; Air Force Sustainment Center; Customer MAJCOM |
| PSM; Concept Developers | Weapon system depot level repairable description; AF Core requirements assessment | Title 10 USC 2366a; Core Applicability Analysis of the Depot Source of Repair (DSOR) Process | DSOR Planning Core Applicability RE: WBS 2.8 | Program Manager; PSM; AFMC/A4; Air Force Sustainment Center |
| Program Manager; PSM | DoDI 5000.02 Milestone A documents that have PS implications | DoDI 5000.02; AFI 63-101/20-101; PS assessment | Milestone A DoDI 5000.02 Requirements RE: WBS 2.9-2.14 | Milestone Decision Authority |

Figure 1. High Level DP Process Flowchart

Figure 2. High Level PS Process Flowchart

Figure 3. Detailed PS Process Flowchart 1.0 in DP – MAJCOM Request to MDD

Figure 4. Detailed PS Process Flowchart 2.0 – MDD to Milestone A

Table 2. WBS

  - Functional DPPST description:

    - The DPPST organizational composition is depicted below in Figure 5.  Though the number of organizations are vast, most DPPST members have a finite role as described in Section 6.  As identified in WBS 1.0 and WBS 2.0, the PS responsibility starts with respective AFLCMC/XZ Division and evolves to the respective PEO Directorate and ultimately the Program Office after MDD.  As the AFLCMC/XZ Division or the PEO Directorate are the responsible members who are executing the majority of the PS workload, the AFLCMC/XZ Division or the PEO Directorate will be the DPPST lead.  The DPPST provides a robust and encompassing functional expertise to assist the lead with PS DP. Some members are considered “core” members, others “subject matter experts,” and others perform a “review” function.  Core members interface with the DPPST for more than a short duration task.  Subject matter experts are involved for typically a short duration task, while reviewers provide their expertise commenting upon programmatic documents.  Note as most DPPST members are subject matter experts for a specific task, it is not envisioned that all DPPST members would meet on a reoccurring basis.  Typically, what is envisioned are a few meetings with a minimal DPPST members for a specific purpose, as most communication will be handled via phone calls and e-mails.  Given TDY budgets, the use of Defense Connect Online and meet-me-lines are the  preferred communication medium for unclassified communications between geographically separated DPPST members.

    - The DPPST will initially focus on PS elements related to the Concept Development process to support the MDD. The DPPST leader is within the respective AFLCMC/XZ Division location where the prospective Program Executive Officer (PEO) portfolio resides, and is APDP Life Cycle Logistics level certified as appropriate for DP effort.  The DPPST team lead, assisted by the DPPST, is typically responsible for the PS strategy and provide Subject Matter Expert (SME) on a number of MDD programmatic documents.  In reference to WBS 1.7, after an MDD date is identified the DPPST team lead will draft up DPPST member specific responsibilities, associated timeframes, and will coordinate with DPPST members.

    - After MDD, the team will focus on PS elements related to the Materiel Solution Analysis phase to support Milestone A.  Ideally, the lead is the senior Program Office Logistician.  If the Program Office is not stood up yet, the Logistics Organizational Senior Functional (LG OSF)  will lead the team.  If a Program Directorate is not assigned, the respective AFLCMC/XZA/C/W organization continues team lead duties.  Once a Program Directorate is assigned, the respective AFMCLC/XZA/C/W office remains on the team in an advisory role.  In reference to WBS 2.1, after MDD and a Milestone A target date is identified, the DPPST team lead will draft up DPPST member specific responsibilities, associated timeframes, and will coordinate with DPPST members.

    - Though not team lead, there is a similar relationship with the Program Office senior Engineer assuming responsibilities from AFLCMC/XZ Engineering, with the Program Directorate Engineering Organizational Senior Functional (EN OSF) involved if a Program Office is not established.  If a Program Directorate is not assigned, AFLCMC/XZ Engineering continues engineering responsibilities.  Once a Program Directorate is assigned, AFLCMC/XZ Engineering remains on the team in an advisory role.

    - The document that describes the technical aspects and top level risks of a concept or family of concepts is the Concept Characterization Technical Description (CCTD).  Typically before the MDD,  CCTD(s) are initially drafted which are then further clarified during the Analysis of Alternatives (AoA) process.  The CCTD document reflects the analytical basis and decision history of concept evolution at a given point in time.  It is within the concept evolution process PS requirements/considerations need to be understood by concept developers and decision authorities.

      - Armed with the CBA/ICD as a starting point, the customer MAJCOM needs to further state any “must have” PS requirements for design considerations.  Note at this point in time, PS requirements should be  generally stated so as not to constrain the concepts.

      - Additionally, experience with analogous weapon systems needs to be considered.  Analogous weapon system performance is researched as the  reliability, availability, and maintainability drivers should be documented.  The associated lessons learned need to be investigated along with PS conclusions and provided to concept developers.  As some of this information may apply beyond Milestone A in the weapon system development process, analogous weapon system notes should be provided to the Program Office to help further shape development considerations before Preliminary Design Review (PDR).

Figure 5. Development Planning Product Support Team Composition

- Measurement.

  - Process Results. Trends from the center’s Logistics Health Assessment (LHA) scores will be used to assess this process.  LHA provides the acquisition and sustainment communities a standard, tailorable, user friendly tool to assess and report on long-term sustainment and availability considerations.  LHA, which is built on the 12 PS elements and is incorporated into System Metric and Reporting Tool (SMART), uniquely covers all program phases to include MDD and Milestone A DP efforts.  All new or existing DP efforts that have a Product Support requirement will perform an LHA.  Once the initial LHA has been performed, this process will continue on a quarterly basis with update required by 30 Dec, 30 Mar, 30 Jun, and 30 Sep of each year.  The DPSST lead will be the primary functional POC for LHA completion. After the assessment, the DPPST lead will seek Program Manager assessment approval (not applicable if the DPPST lead is the Program Manager).  As LHA utilizes SMART for reporting, the DP effort will be identified as an “activity” within SMART so as not to trigger additional programmatic reporting requirements.

  - Process Evaluation.  LHA data, to include trends, will be reviewed quarterly by AFLCMC/LG.  The DPPST lead will assess overall PS progress through the LHA process on a quarterly basis, and share with the Program Manager at a minimum.  The DPPST lead and/or the Program Manager can suggest any changes to the LHA process in order to improve the assessment effort.

- Roles and Responsibilities

  - The following office identification and associated roles/responsibilities are envisioned as typical, but not absolute.  Specific DPPST member tasks will be defined, documented, and coordinated on a specific DP effort as outlined within WBS 1.4.8.3 and WBS 2.1.

  - AFLCMC/XZA (Aero Systems Development), AFLCMC/XZC (Electronic Systems Development), and AFLCMC/XZW (Armament Systems Development) before MDD will:

    - Be the DPPST Lead and secure appropriate LCL APDP certification

    - Develop agendas, orchestrate meetings and calendar of events

    - Coordinate with DP Program Manager documents to be assessed for PS implications; provide initial assessment before releasing to the team

    - Coordinate analogous Product Support Manager (PSM) support for historical weapon system performance and PS lessons learned (positive and negative)

    - Draft the initial PS Strategy for team review (section in the Life Cycle Sustainment Plan)

    - Draft and coordinate the DPPST tasks

  - PEO Directorate Logistics Organizational Senior Functional/Program Office Logistics (if Program Directorate not assigned, AFLCMC XZA/C/W) after MDD will:

    - Be the PS Team Lead

    - Develop team agendas, orchestrate team meetings and calendar of events

    - Coordinate with Program Manager documents to be assessed for PS implications; provide initial assessment before releasing to the team

    - Document the initial Life Cycle Sustainment Plan for team review

    - Consult with Legal Counsel concerning the Technical Data Rights Strategy; draft initial technical data rights strategy for team review

    - Execute the DSOR planning Core applicability

    - Provide Request For Proposal assessment

    - Draft and coordinate DPPST tasks

    - Consider if a PS Business Case Analysis (BCA) is applicable (possible if commercial application derivative)

    - Consult with AFLCMC/XZA, XZC, or XZW as required

  - AFLCMC/XZ Engineering (Engineering & Analysis) will:

    - Lead technical analysis assessing technical feasibility, performance, cost, schedule, and risk of weapon system concepts

    - Coordinate XZ Engineering resource requirements for PS purposes

    - Document Concept Characterization and Technical Descriptions (CCTDs) for MDD purposes

    - Note:  “XZ Engineering” refers to Wright-Patterson XZE, Hanscom XZC,  and Eglin XZW engineering offices

  - PEO Directorate Engineering Organizational Senior Functional/Program Office Engineering (if Program Directorate not assigned, AFLCMC XZ Engineering) after MDD will:

    - Document the Reliability, Availability, Maintainability and Cost (RAM-C) Rationale Report

    - Finalize and document CCTDs for Milestone A purposes

  - AFLCMC/XZI (Materiel Integration) will:

    - Provide initial PS Strategy and CCTD review

  - Customer MAJCOM (typically A4; A2/5/6/8 (when deemed appropriate by MAJCOM)) will:

    - Provide CBA PS interpretation and documentation

    - Provide ICD PS interpretation and sustainment requirements documentation

    - Provide operational CONOPS, maintenance and support CONOPS, to include operating environments

    - Provide PS requirements before MDD

  - AFMC/A4D (Depot Operations) will:

    - Provide Core Applicability Analysis and Candidate Depot assignment(s)

  - AFMC/A4U (Life Cycle Management) will:

    - Provide HQ AFMC coordination on the initial Life Cycle Sustainment Plan (LCSP)

  - AFMC/A5C (Capability Planning & Requirements) will:

    - Provide review of JCID documents

  - AFMC/A9A (Studies and Analysis) will:

    - Provide independent input to and review of analysis methodologies

  - OAS/A9A (AFMC; Office of Aerospace Studies) will:

    - Provide technical and analytical guidance concerning Analysis of Alternatives (AoA) and AoA related studies

  - AFSC/LGX (Strategic Plans, Policies, and Processes) will:

    - Provide analogous weapon system performance/repair information when information is resident within AFSC databases.  Information will be requested to AFSC/LGX via the analogous weapon system PSM.

    - Provide information to support the Strategic Source of Repair process

    - Provide strategic supply chain management assessment as described within the LCSP

    - Provide initial LCSP review

Note – Subject Matter Expert pre-MDD; Core member after MDD

  - AFLCMC/LG/LZ (Logistics) will:

    - Provide Subject Matter Expert support for logistical functional areas

    - Provide initial PS strategy review

    - Provide initial LCSP review

  - AFLCMC/INA/C/M (Acquisition Intelligence) will:

    - Provide Subject Matter Expertise (supply chain threat assessment; critical program protection; additional planning factors)

    - Provide initial LCSP review

  - AFLCMC/AQT (Center Test Authority) will:

    - Provide Test & Evaluation Strategy expertise relative to PS

    - Provide initial LCSP review

  - AFLCMC/EZP (Product Support Engineering)will:

    - Provide Reliability and Maintainability (R&M) analyses expertise

  - AFLCMC/EZJ (Systems Analysis) will:

    - Support Availability analysis

    - Provide Operational analysis expertise

  - AFLCMC/WNV (Environment, Safety, and Occupational Health (ESOH)) will:

    - Provide ESOH expertise

- Tools.

  - Acquisition Workbench.  SMART and LHA reside within the Acquisition Workbench under Core Acquisition Tools.  The Acquisition Workbench can be found at:

https://af-aqweb.deps.mil/Pages/default.aspx

(Note: use e-mail certification)

  - AFMC/AFSPC Development Planning. DP references can be found at:

https://cs3.eis.af.mil/sites/OO-XP-MC-94/AFKN_Docs/Forms/AllItems.aspx?RootFolder=%2Fsites%2FOO%2DXP%2DMC%2D94%2FAFKN%5FDocs%2FTools&FolderCTID=0x0120009BC7C4372671784B9DD72FA19E06CABD&View=%7bC49B9973-9EC2-43F1-9C7D-D64EC1D8FAFC%7d

  - Product Support Tool Kit (PSTK).  The PSTK is a helpful PS resource.  PSTK can be found at:

https://cs3.eis.af.mil/sites/MC-LG-01-82/default.aspx

- Training.

  - Training Plan. This process is available on the AFLCMC Process Directory.  A PowerPoint presentation will be briefed as necessary to educate perspective DPPST leads.  Upon request, AFLCMC/XZ will facilitate DPPST leads in developing and documenting their DP effort.

  - Available Training. There are no official training classes for this process; however, AFLCMC/XZ will facilitate DPPST leads in developing and documenting their DP effort.  LHA functional training is available via the SMART program office, and periodically through AFLCMC/LG.  The web based LHA training is located on the SMART home page under "web based training” at:

https://usaf-acq.platform.milcloud.mil/SMART/smart_app/Workspace.aspx

- Definitions, Guiding Principles and/or Ground Rules & Assumptions. The relationship between this standard process and the AFLCMC Development Planning standard process is the Pre-Milestone A Product Support process is a subset of the Development Planning  process.  WBS 1.0 elements are the actual Development Planning WBS numbers.

- References to Law, Policy, Instructions or Guidance.

  - Title 10 USC 2366a

  - DoDI 5000.02, Operation of the Defense Acquisition System, 8 Dec 2008

  - AFI 63-101/20-101, Integrated Life Cycle Management, 7 Mar 2013

  - AFPAM 63-128, Guide to Acquisition and Sustainment Life Cycle Management, 5 Oct 2009

  - OSD Defense Acquisition Guidebook,  https://dag.dau.mil/Pages/Default.aspx

  - OSD Product Support Manager Guidebook, Apr 2011

  - OSD Integrated Product Support Element Guidebook, Dec 2011

  - OSD Memo, Document Streamlining – Life Cycle Sustainment Plan, 14 Sep 2011

  - Concept Characterization and Technical Description (CCTD) Guide, SAF/AQ, 27 Oct 2010

  - DoD Guide for Achieving Reliability, Availability, & Maintainability, 3 Aug 2005

  - DoD  Reliability, Availability, and Maintainability, and Cost Rational Report Manual, 1 June 2009

  - AFMC Development Planning Guide, 17 June 2010

Attachment 1: WBS

# Text boxes

Air Force Life Cycle Management Center (AFLCMC)

Standard Process

for

Pre-Milestone A Product Support

Process Owner:  AFLCMC/XZ

Date: 16 Jun 2015

Version: 1.2