## Slide 1
Selected Acquisition Report (SAR)
Maj Kyle Reybitz
SAF/AQXRR
as of 19 Jan 10

## Slide 2: Outline
Definition and Requirements
Purpose and Uses
Content
Dec 09 SAR List
Dec 09 SAR Schedule
Process
Dec 09 Nuances
Summary

## Slide 3: SAR Definition and Requirements
What is a SAR?
  A standard, comprehensive summary reporting of schedule, performance, and cost information on Major Defense Acquisition Programs (MDAPs) within the Department of Defense (DoD) and to the Congress.
Statutory Requirement
  Title 10, Sec. 2432
Regulatory Requirement
  DoDI 5000.02
Reported “Quarterly”
  Dec: Annual for all MDAPs (currently 32 AF Programs)
    report submitted to Congress 60 days after PB submission
  Mar, Jun and Sep: by exception/out-of-cycle
    Nunn-McCurdy Unit Cost Breach
    >6 month schedule delay in the Current Estimate (CE) since last SAR
    Initial SAR (“quarter” following Milestone B decision)
    Termination SAR (>90% expended or delivered)
    Rebaselining from one Major Milestone to the next

## Slide 4: SAR Purpose and Uses
Purpose
  Provides status of an MDAP at a specific moment in time while documenting accomplishments, updating program information and explaining variations from previous reports
Deliverable to Congress
  First source of information for staffers, committees, etc.
  Publically accessible through FOIA requests
Authoritative source for MDAP information
  Frequently accessed by all levels of DoD
  Various elements analyzed to develop metrics and assess progress/health

## Slide 5: SAR Content
SECTIONS
1. Program Information
2. Responsible Office
3. References
4. Mission & Description
5. Executive Summary
6. Threshold Breaches
7. Schedule
8. Performance
9. Track to Budget
10. Cost & Funding
11. Low Rate Initial Production
12. Foreign Military Sales
13. Nuclear Costs
14. Unit Cost
15. Cost Variance*
16. Contracts
17. Deliveries & Expenditures
18. Operating & Support Costs
19. Classified Annex (if required)
COMPARED TO QUARTERLY DAES
RED – mostly overlapping data
GREEN – partially overlapping data
BLUE – mostly unique data
* Cost Variance most time consuming
1-3
4-5
6
7
8
9
10
11-13
14
15
16
17
18
(19)

## Slide 6: Where are SARs?
Created/stored in Defense Acquisition Management Information Retrieval (DAMIR)
  OSD’s System to store/ authoritative source of:
    APBs
    SARs
    DAESs
    Other
  Role based access/privileges
    PMO, PEO, AQ, OSD
    Basic, Review, Editor, Release
  Access thru AQXRR available for the following:
    Gov’t civilians
    Military
    Support Contractors (request must come from Civ/Mil)
http://www.acq.osd.mil/damir/

## Slide 7: Dec 09 SAR Programs 31 Total
PEO/AC (11)
C-130 AMP
C-130J
C-17A
C-5 AMP
C-5 RERP
JCA
LAIRCM
B-2 EHF
B-2 RMP
F-22
JPATS
PEO/SP (8)
SBIRS-HIGH
SBSS BLK 10
AEHF
FAB-T
GBS
WGS
GPS IIIA
NAVSTAR GPS
PEO/ES (1)
NPOESS
DAO/AFNWC (1)
Minuteman III PRP**
PEO/WP (3)
AMRAAM
JASSM
JDAM
PEO/C2&CS (2)
MP-RTIP
NAS
*Initial SARs
** Termination SARs
SAF/AQXRR POCs
Mr. Alan Lachel, alan.lachel@pentagon.af.mil DSN 260-0374
Maj Kyle Reybitz, kyle.reybitz@pentagon.af.mill DSN 260-0375
Maj Mark Murray, mark.murray@pentagon.af.mill DSN 260-0367
Mr. Bob Loop, robert.loop@pentagon.af.mill DSN 260-0365
PEO/ISR (4)
ASIP*
RQ- 4 Global Hawk
MQ-1 Predator*
MQ-9 Reaper*
PEO/JSF (1)
F-35
WI
WI
AP
WI
WI
AP
HC
WI
WI
WI
HC
DJ
MM
DJ
HC
LA
DJ
DJ
DJ
OSD/AT&L ARA AM POCs
LA – Mr. Larry Axtell, 703-695-5167
WI – Mr. Wendel l Irby, 703-695-9692
AP – Mr. Andy Pozda, 703-571-3116
HC – Mr. Harry Chelpon, 703-614-0200
DJ – Mr. Derek Jaquish, 703-571-3118
MM – Ms. Margaret Mattei, 703-571-3117
MB – Mr. Mike Burke, 703-697-0452
JW – Mr. James Wessels, 703-697-3383
MM
MM
DJ
DJ
AP
MB
AP
HC
AP
HC
MM
JW

## Slide 8: Dec 09 SAR Schedule
25
18
5
1
8
15
22
1
8
15
22
29
Reports due to OSD (17 Feb)
OSD Final Review (11-18 Mar)
February
March
12
Reports due to AQXR (8 Feb)
Security Review & SAR Classified
Annex copies (22-26)
OSD to Congress (2 Apr)
Telcons (3-10 Mar)
PMO Corrections (9-16 Mar)
OSD SAR Memo (13 Jan)
PMOs Enter SAR in DAMIR
PEOs release (1 Jan – 8 Feb)
FY11 Budget (1 Feb)
January
April
AQXR Review (9-17 Feb)
PMO/PEO OPR
AQXRR OPR
OSD OPR
PMO & AQXRR OPRs

## Slide 9: SAR Process
AT&L Memo
OSD
PEO
PMO
AQX Memo
PEO Instructions
Generate SAR
PEO Inputs to AQX
Provide
PB Funding
Inflation Indices
AQX Review
OSD Review
Teleconference
Review
OSD
SPO
AQX
PEM
USA
Incorporate
Revisions
Final
AQ Submission
OSD Review
& Submission
to Congress
Security Review
Submission to OSD
AQ

## Slide 10: SAR – AQXR Role
Coordinate with OSD, PEOs and PMOs
  Support telcons with PMOs, OSD & AQX
    Also PEM and PEO staffs in some cases
  Package and process classified annexes
Quality check of documents
Manage back-and-forth activity between Air Force and OSD

## Slide 11: Dec 09 SAR Considerations
Dec 09 SARs expected to document accomplishments and variances since Dec 07 SARs
  Dec 08 “Limited” SARs are available upon request to SAF/AQXRR but are not stored in DAMIR
Weapons System Acquisition Reform Act (WSARA) 2009 Impacts TBD (expect guidance from OSD)
  DTM 09-027, Section 5e. “For MDAPs, the confidence level statement shall be also included in the next selected acquisition report (SAR)…”
  Confidence Level (CL) statement describes the CL used in establishing the cost estimate, the rationale for selecting the CL and if the CL is less than 80 percent, the justification for selecting the lower confidence level.
Dec 09 SARs need to be consistent with PB11 FYDP and J-Books
  Numbers may not match exactly but variations need to be explained

## Slide 12: SAR - Summary
SAR is a PMO deliverable/report to Congress due 60 days after release of PB (forecasted for 1 Feb 10)
SAF/AQX is the SAR Service Point of Contact; facilitator between PEO/PMO and OSD
Initial SAR submissions for all MDAPS due to SAF/AQXRR by 8 Feb 10; early start is key!
  AF Inflation indices sent 12 Jan, Army/Navy indices sent 13 Jan
  Official “SAR Kickoff” Memo from SAF/AQX (including OSD Memo w/Dec 09 SAR specifics) sent week of 25 Jan 10

## Slide 13: BACK-UP

## Slide 14: APB & Nunn-McCurdy Background
Purpose: To provide Congressional unit cost reporting for Major Defense Acquisition Programs (MDAPs) that are submitting Selected Acquisition Reports (SARs) (except MDAPs reporting RDT&E only costs prior to Milestone B)
Applicable Statute: Title 10, United States Code, Section 2433 (Unit Cost Reports) and Section 2435 (Baseline Description)
Unit Cost Measurements (in base-year dollars):
  PAUC (Program Acquisition Unit Cost)
  = (RDT&E $ + Procurement $ + MILCON $ + Acquisition-Related O&M $) / Total Quantity
  APUC (Average Procurement Unit Cost)
  = Procurement $ / Procurement Quantity
Unit Cost Tracking: Compare Current Estimate to Current Baseline Estimate and to Original Baseline Estimate
  Current Estimate – Latest estimate of approved program
  Current Baseline Estimate – Currently approved Acquisition Program Baseline (APB)
  Original Baseline Estimate – APB approved at Milestone B (or initial MDAP APB if designation occurs after Milestone B)
  Note: Original Baseline Estimate can be revised only after “Critical” Nunn-McCurdy breach.

## Slide 15: APB & Nunn-McCurdy Breaches
Reporting Requirements:
  Internal – Quarterly unit cost reporting required from program manager to Service Acquisition Executive via Defense Acquisition Executive Summary (DAES)/Web Services
  External – Breach reporting (see below)
For “Significant” breaches, Service Secretary must notify Congress within 45 days of the report (normally PDR) upon which the determination is based and submit a SAR with the required additional unit cost breach information
For “Critical” breaches, in addition to notification and SAR, the USD(AT&L) must certify to Congress within 60 days of the SAR that:
  1. The program is essential to the national security
  2. There is no alternative which will provide equal or greater capability at less cost
  3. The new estimates of the PAUC and APUC are reasonable
  4. The management structure is adequate to control PAUC and APUC
  (Note: Certification not required for terminated program)
If either SAR or certification are not submitted on time, obligational authority suspended on all major contracts
 | “Significant Breach” | “Critical Breach”
Current Baseline Estimate | +15% | +25%
Original Baseline Estimate | +30% | +50%

## Slide 16: SAR - PEM Participation
Beneficial if PEMs are involved in telcons
  Prep– review their SAR; ID needed changes
  Attend telecon, provide inputs
Following the telcons
  Process is mostly administrative
  Minimal PEM involvement
    If something is broken, PEM should let us know